## Sheet1
# | task | target date | impact date
1 | .Timestamp from PBSA is defaukt and it is 00:00:00 | 810353 | 810353
2 | .PR Lines can not be created from PBSA Head Office test instance and so that Oracle can not complete the interated test on PR Lines and Supplier Return Requests | 810353 | 810353
3 | .tax(eg. VAT)\cost calculation after GRN\PO for the MRP value of the product | 810353 | 810353
4 | .Product wise sales\payments summary or Product Category wise | 810353 | 810353
5 | .Initial upload of GUIDs for products and suppliers | 810353 | 810353
6 | .Head Office endpoints for supplier, is it supposed to be 2-way? And handle the queue of updated data towards PBSA | 810353 | 810353
7 | .Regression test plan with Outlet IP list | 810353 | 810353
8 | .return waste(% of value of return stock)\non waste | 810353 | 810353
9 | .stock count | 810353 | 810353
10 | .delivery location changeof the PR\PO\GRN levels | 810353 | 810353
11 | .Test Summary for MD070 Ref. | 810353 | 810353
12 | .Data Conversion Doc | 810353 | 810353
13 | .Tech manual | 810353 | 810353
14 | .OAuth (and hosted in Azure) | 810383 | 810383
15 | .grant username/password | 810383 | 810383
16 | .Bearer JSON request from PBSA JSON response from Oracle | 810383 | 810383
17 | .integrations: 1. stores 2. products 3. purchase-requests (developed incorrect) 4. supplier-return-requests (developed incorrect) (5. supplier (developed incorrect)) | 810383 | 810383
18 | .Head Office Event OAuth via Oracle JSON response integrations: 1. PRs from outlets consolidated to a purchase-order lines and on approval event (ws_getpo.sql) 2. Return Note supplier-returns and on return event 3. PR rejected-lines and on reject event 4. Supplier data new or modification and on create/update event | 810383 | 810383
19 | .Outlet Relational Schema for Report Request and Oracle Interface\API (use caching\filtering with Queues) | 810383 | 810383
20 | .Receive data for GL entries and store in given model (Ref: Relational Schema) 1. Sales and Payments 2. Stock 3. Tills | 810383 | 810383
21 | .View the data General 1. store data | 810383 | 810383
22 | .Sales 1. sales data | 810383 | 810383
23 | .data flush policy from APEX server | 810383 | 810383
24 | .grab all the data dependencies (PO created with all\few outlet PR lines, JE entry based)\ | 810383 | 810383
25 | .R&TD inputs from Sathosa\softwatch\Oracle Tech Team\PBSA (eg. data security)\ | 810383 | 810383
26 | .whitelist IP but communication protocol | 810383 | 810383
27 | .mapping to POS product and inventory\ | 810383 | 810383
28 | .back-dated sales invoke explicitly daily) | 810383 | 810383
29 | .data views: to PBSA\ | 810383 | 810383
30 | .stores, products, purchase-requests (developed incorrect), supplier-return-requests (developed incorrect), Return Note supplier-returns and on return event, PR rejected-lines and on reject event, Supplier data new or modification and on create/update event | 810383 | 810383
31 | .interfaces\api: inventory categories, items\products, suppliers\ | 810383 | 810383
32 | .block diagram to MD.070 | 810383 | 810383
33 | .Dashboard to intermediate server - Oracle JET | 810383 | 810383
34 | .PKG-MAIN token\access_type\expires_in variable | 810383 | 810383
35 | .PKG-ORACLE-EBS database link (daily creation of EBS records from imported data in intermediate server) views (for exposing webservice) | 810383 | 810383
36 | .PKG-INTERMEDIATE-SERVER token (schedule based in expires_in) request data import data scheduler tables database link (pull data for exposing webservice) | 810383 | 810383
37 | .EBS Stores, first 5 item category? | 810383 | 810383
38 | .Exception Report email | 810383 | 810383
39 | .APEX Dashboard | 810383 | 810383
40 | .Item\Category Import\, UoM???, template for categories? *run item import. | 810383 | 810383
41 | .Create views\ | 810383 | 810383
42 | .Refresh reports in sqldeveloper X | 810383 | 810383
43 | .IP addresses list (outlets IP, HO IP after api work) | 810383 | 810383
44 | .purchase-orders->send to ho | 810383 | 810383
45 | .supplier-returns->send to ho | 810383 | 810383
46 | .rejected-lines->send to ho | 810383 | 810383
47 | .suppliers->send to ho | 810383 | 810383
48 | .stores->send 200 | 810383 | 810383
49 | .products->send 200 | 810383 | 810383
50 | .purchase-requests->give in model format to Oracle\need to connect in to outlets | 810383 | 810383
51 | .supplier-return-requests->give in model format to Oracle\need to connect in to outlets | 810383 | 810383
52 | .ws templates/ | 810383 | 810383
53 | .REST API call package (token\, and data from outlets:old PBSA or from ho\ if new PBSA) | 810383 | 810383
54 | .db links to Interface\API staging tables (JE...\, PR\) | 810383 | 810383
55 | .db links from EBS base tables (PO,Rejected Lines, Reverse GRN, Supplier) and table updates after sending data\ | 810383 | 810383
56 | .db links from EBS base tables (stores, products) and table updates after sending data\ | 810383 | 810383
57 | .Master data upload Supplier\Item\Assign to categories\ | 810383 | 810383
58 | .DFF to CoF Store ID\Location\Store ID x | 810383 | 810383
59 | .after debit memo created in AP Supplier return approved | 810383 | 810383
60 | .JE categories with control accounts for sales\payments\bank-deposits\tills \ | 810383 | 810383
61 | .sending PBSA PO number and Oracle EBS PO number mapping | 810383 | 810383
62 | .(AR receipt based on credits to outside parties) | 810383 | 810383
63 | .supplier return from cost\quantity\lines etc.\ | 810383 | 810383
64 | .Supplier Agreement Table for error msg on Integration Program | 810383 | 810383
65 | .Date with time in next patch. PBSA informed.\ | 810383 | 810383
66 | .supplier/product GUID update\ | 810383 | 810383
67 | .item category/CoA Segment validation for location\product\product category for JE\ | 810383 | 810383
68 | .Exception Report Outlet wise\# records wise (running import program 2 times restriction using a PK, EBS staging update apex need to control from PBS s/w) | 810383 | 810383
69 | .Master Data upload ~Item upload OIN succeed and assign interface test | 810383 | 810383
70 | .data from outlets:old PBSA - IP addresses list (outlets IP, HO IP after api work). | 810383 | 810383
71 | .after debit memo created in AP Supplier return approved.\\ | 810383 | 810383
72 | .EBS Stores, first 5 item category? UoMs inital upload of GUIDs. | 810383 | 810383
73 | .Exception Report email. | 810383 | 810383
74 | .APEX Dashboard. | 810383 | 810383
75 | .data flush policy from APEX server (related to Oracle costing\tax etc.). | 810383 | 810383
76 | .R&TD inputs from Sathosa\softwatch\Oracle Tech Team\PBSA (eg. data security) - whitelist IP but communication protocol. | 810383 | 810383
77 | .return waste(% of value of return stock)\non waste | 810383 | 810383
78 | .supplier v1 template to products(1st)\PO\SUP Ret\supplier return? after debit memo - need to confirm \\ | 810383 | 810383
79 | .JE update status flag\ | 810383 | 810383
80 | .Exception Report Outlet wise\# records wise (running import program 2 times restriction using a PK, EBS staging update apex need to control from PBS s/w) | 810383 | 810383
81 | .Master Data upload ~Item upload OIN succeed and assign interface test /both INV ORGs | 810383 | 810383
82 | .Ask from PBSA S/W Team | 810383 | 810383
83 | .:body(POST empty or else) of the supplier update endpoint like in rejected lines\supplier return\PO | 810383 | 810383
84 | .confirm the po_reference | 810383 | 810383
85 | .MrpIncTax\TaxCode in supplier return\PO | 810383 | 810383
86 | .Naming convention to JE batch\entry | 810383 | 810383
87 | .Printer Setup | 810383 | 810383
88 | .w/o PO reject - debit memo and misc transfer (1.Interstock - w/wo PO 2.To vender - w/wo PO ) | 810383 | 810383
89 | .hyper-v user admins | 810414 | 810414
90 | .SSO for Oracle applications | 810414 | 810414
91 | .Timeout notification for pending Approvals (WFs) | 810414 | 810414
92 | .PBSA data imports after weekends-needs to be handled/ | 810414 | 810414
93 | .XXPBSA_EXECUTE_IMPORT_PRC with parameter if failed in schedule and needs implicit running | 810414 | 810414
94 | .Master Data (Supplier and Item with a ".", tax calc flag for the item) 1/2 | 810414 | 810414
95 | .Debtor movement no aging/file based solution for possible aging | 810414 | 810414
96 | .Gift Vouchers are for AR invoices based on Payment taking and creating 1/2 | 810414 | 810414
97 | .API Testing-JE | 810414 | 810414
98 | .API Testing-Product (Taxes - for sales only and not for POs and POR flags) | 810414 | 810414
99 | .API Testing-rejected-lines | 810414 | 810414
100 | .Gift Vouchers are for AR invoices based on Payment taking and creating | 810414 | 810414
101 | .Printer Service PDF - Oracle Applications Character Printing (Doc ID 112172.1) Severity 1 | 810414 | 810414
102 | .Outlet mapping and GRN number prefix with shop codes (GRN Report needs to run and see) | 810414 | 810414
103 | .credit period based on supplier brought invoice date | 810414 | 810414
104 | .Regression Testing readiness (Authentication Certification sh+ Token PL/SQL) | 810414 | 810414
105 | .Product Movements with reason code (like spoil, stolen, ) | 810414 | 810414
106 | .AP Invoice Batch name payment term\user\Pay Group (super user with all batch) | 810414 | 810414
107 | .API Testing-Interstock | 810414 | 810414
108 | .OTHER Pay group | 810414 | 810414
109 | .Supplier return request approval to DGM Operations-retun with auto approval/send approved requests | 810414 | 810414
110 | .DFFs for supplier and item (GUID, user, Taxes, PO cancellations)/ | 810414 | 810414
111 | .Buyer prompt changed Logged "User"/ | 810414 | 810414
112 | .PO Free qty / | 810414 | 810414
113 | .Summary JE Balance X - JE Web ADI | 810414 | 810414
114 | .AP Invoices\JEs userwise/ | 810414 | 810414
115 | .AP invoice sequencing / | 810414 | 810414
116 | .AP invoice track asset tick based on previous asset GRN | 810414 | 810414
117 | .Receiving control default based on item category and category based (GROCERY CATEGORY) PO cancellation duration in Item Master DFF / | 810414 | 810414
118 | .supplier return pending report-exception report | 810414 | 810414
119 | .supplier Return Report-exception report | 810414 | 810414
120 | .Sales Reports/ | 810414 | 810414
121 | .Operational Reports???/ | 810414 | 810414
122 | .WHT at payment point (item level) | 810414 | 810414
123 | .charges (item wise) | 810414 | 810414
124 | .AP invoices with cash clearing ... | 810414 | 810414
125 | .create the debit memo inside the invoice batch 1/2 | 810414 | 810414
126 | .JSON output for successful operation response as agreed | 810414 | 810414
127 | .head office\products apis testing rejected-lines 1/2 | 810414 | 810414
128 | .Printer Service PDF 1/2 | 810414 | 810414
129 | .AP invoice track asset tick based on previous asset GRN | 810414 | 810414
130 | .Outlet mapping-sent | 810414 | 810414
131 | .credit period based on supplier brought invoice date ++ | 810414 | 810414
132 | .Regression Testing readiness*** | 810414 | 810414
133 | .Product Movements with reason code (like spoil, stolen, ) | 810414 | 810414
134 | .Debtor JE 1/2 | 810414 | 810414
135 | .Provide My Oracle Support for Finance Heads-sent | 810414 | 810414
136 | .PO Free qty | 810414 | 810414
137 | .Receiving control default based on item category and category based (GROCERY CATEGORY) PO cancellation duration in Item Master DFF | 810414 | 810414
138 | .GRN number prefix with shop codes | 810414 | 810414
139 | .free qty. | 810414 | 810414
140 | .minus tolerance invoice | 810414 | 810414
141 | .Batch name user should be updatable from supplier creation, search based on user | 810414 | 810414
142 | .exception report from integration 2 points | 810414 | 810414
143 | .payment terms based batches | 810414 | 810414
144 | .Category wise GRO and PRO batches (based on supplier pay group or item category) | 810414 | 810414
145 | .tax level supplier and item | 810414 | 810414
146 | .OTHER Pay Group code | 810414 | 810414
147 | .Duplicate Supplier Invoice Number if not Sathosa did | 810414 | 810414
148 | ."Reprinted" tag | 810414 | 810414
149 | .Supplier return request approval to DGM Operations-retun with auto approval/send approved requests | 810414 | 810414
150 | .Item Categories data dump fix / | 810414 | 810414
151 | .Supplier Return Request Approval Criteria | 810414 | 810414
152 | .Buyer prompt changed Logged "User" | 810414 | 810414
153 | .Invoice batch assign X super super with all batch | 810414 | 810414
154 | .functional configs | 810414 | 810414
155 | .transport charges from warehouse based point grn, cold chain other charges point grn from item category-need logic | 810414 | 810414
156 | .Asset location and Purchasing Locations-two categories (item master is assigned with details - 12 Nov 2018) | 810414 | 810414
157 | .Quatation+CWE/IT Asset -> Finance FA??? | 810414 | 810414
158 | .Asset Register with Invoice Number??? | 810414 | 810414
159 | .Timeout notification for pending Approvals??? | 810414 | 810414
160 | .payment for a total of 100k etc | 810414 | 810414
161 | .supplier upload/item upload verify the functionalities??? | 810414 | 810414
162 | .ap inv approval based on the value on hold??? | 810414 | 810414
163 | .ap inv solution requirement/ folder options??? | 810414 | 810414
164 | .min(supplier invoice, created inv) tolerance set off??? | 810414 | 810414
165 | .min(supplier invoice, created inv) tolerance set off??? | 810414 | 810414
166 | .initial float in outlet??? | 810414 | 810414
167 | .check number seq based on the bank??? | 810414 | 810414
168 | .check seq define\role required??? | 810414 | 810414
169 | .important concurrents like Open Int Program failure notification email??? | 810414 | 810414
170 | .PO Qty level freeze and PO Super User excluded - Responsibility Matix??? | 810414 | 810414
171 | .creditor is created after the GRN is done/aging on AP accrual???-need validation | 810414 | 810414
172 | .Engineering & Operations Procurement to PO Dept. (Spec from FA Finance to Procurement do purchasing quality check\GRN to FA Procurement)?? | 810414 | 810414
173 | .petty cash with a dummy bank A/C | 810414 | 810414
174 | .Asset creation and Payment delay but asset is used. No issue will occur?? | 810414 | 810414
175 | .Tax hitting accounts of Asset Invoice?? | 810414 | 810414
176 | .show only user created JEs | 810414 | 810414
177 | .Invoice Number from a personalize Invoice sequence-LSLOP editiable | 810414 | 810414
178 | .AP Invoice upload for head office (Utility) | 810414 | 810414
179 | .doc seq for JE,AP,etc | 810414 | 810414
180 | .Gift Vouchers from AP | 810414 | 810414
181 | .i owe you-misc receipt(1)-A/Cs wise and Common | 810414 | 810414
182 | .Outletwise Supplier created and AP invoice for Petty Cash (float is maintained with reimbusment)(2) | 810414 | 810414
183 | .Sales with VAT only not NBT needs testing + Purchases with VAT+NBT (recoverable & non-recoverables) | 810414 | 810414
184 | .Debtor file based solution | 810414 | 810414
185 | .Inter-Stock Transfer Variation JE (SrcCr- RecDr-) and Price Adjustment\Product Movement JE/ | 810414 | 810414
186 | .VAT NBT distributions api change ETA/ | 810414 | 810414
187 | .PO Approvals/PO Responsibility Matrix / | 810414 | 810414
188 | .Delivery Note Format***/ | 810414 | 810414
189 | .Sales TAX components for Sales/ | 810414 | 810414
190 | .PBSA and Sathosa Item Master diff/Promotional item identification (diff item code or something)/ | 810414 | 810414
191 | .Item Upload precedence flag or template/ | 810414 | 810414
192 | .Quatation+CWE/IT Asset -> Finance FA/ | 810414 | 810414
193 | .Engineering & Operations Procurement to PO Dept. (Spec from FA Finance to Procurement do purchasing quality check\GRN to FA Procurement)??? | 810414 | 810414
194 | .ITEM LEVEL Asset Category for Invoice/ | 810414 | 810414
195 | .Oracle Documentation with workflows/ | 810414 | 810414
196 | .Buyer prompt changed Logged "User"/ | 810414 | 810414
197 | .Tax in invoice level/ | 810414 | 810414
198 | .neeed by date based PO cancellation/ | 810414 | 810414
199 | .asset supplier except to PBSA POS (supplier\item creation by Finance)+Asset Item creation for Finance/ | 810414 | 810414
200 | .Outlet level services from PBSA POS/ | 810414 | 810414
201 | .hold notification to management based on a scheduled time / Month-end process proposed-timeout/ | 810414 | 810414
202 | .Asset location and Purchasing Locations/ | 810414 | 810414
203 | .Asset creation and Payment delay but asset is used. No issue will occur/ | 810414 | 810414
204 | .Tax hitting accounts of Asset Invoice/ | 810414 | 810414
205 | .change inv number after GRN inv (duplicate pay on receipt autorun program or profile option update to ap inv number from PO-Supplier_INV_No)\ | 810414 | 810414
206 | .ap invoice number should be ExternalReferenceNumber of the GRN\ | 810414 | 810414
207 | .AR expenses 1%/ Manual Process from Finance\ | 810414 | 810414
208 | .cheque return\late payment on termsX | 810414 | 810414
209 | .period closure based on manual docs from outlet. is Bank statement and AP\AR reconciliation not sufficient?X | 810414 | 810414
210 | .payment will come as a customer in PBSA. X\customer codes required | 810414 | 810414
211 | .AR lockbox auto apply receipt X | 810414 | 810414
212 | .codes of debtors X | 810414 | 810414
213 | .Supplier Return invoiced based on the last approved PO / | 810414 | 810414
214 | .auto inv validate/approve/ | 810414 | 810414
215 | .payments based on the voucher number/ | 810414 | 810414
216 | .supplier invoice number will be available in the Payment Voucher and persists against the invoiceX | 810414 | 810414
217 | .supplier can be changed when the time of approval\on wards so that PO is not fixed/ | 810414 | 810414
218 | .POS inv number will be the supplier invoice that he brings. need to enter the supplier brought inv number at the time of the Payment Voucher print then Oracle saves it for future reference. X | 810414 | 810414
219 | .credit sales with the diff of all sales and credit payment (JEs)/ | 810414 | 810414
220 | .PO concern/ | 810414 | 810414
221 | .duplicate of PR lines when saving after initial tdone | 810414 | 810414
222 | .locations in POs\ | 810414 | 810414
223 | .supplier types for batches\ | 810414 | 810414
224 | .Station\drugs\genral\house hold except from segment4/ | 810414 | 810414
225 | .PO charge account segment2 from mtl_items_kfv\logically required/ | 810414 | 810414
226 | .avg cost x for POs and Supplier Return data fix schedule OR PO response from ho endpoint/ | 810414 | 810414
227 | .Item creation add to /products endpoint (confirm the endpoint to PBSA)\ | 810414 | 810414
228 | .CM swiftx... format (unreconciled to JE entries A)/ Excel can be used with Bank Codes analyzed previous records | 810414 | 810414
229 | .TB mapping/ | 810414 | 810414
230 | .backlog entering (starting from cutover) - PO\GRN\INV - KPMG Team will works with LSL/ | 810414 | 810414
231 | .November Closed Periods and Adjustments will be in th future periods/ | 810414 | 810414
232 | .Balance Sheet balances with Liabilities\AP inv debit/ | 810414 | 810414
233 | .Inventories balances from the Manual Entries/ | 810414 | 810414
234 | .AR recon. with misc automatically/ | 810414 | 810414
235 | .AP recon - AP Accrual A/C (GRNs not invoiced)/ | 810414 | 810414
236 | .Mock cutover/ | 810414 | 810414
237 | .Extenal Ref. update field is same/ | 810414 | 810414
238 | .TAX distributions/ | 810414 | 810414
239 | .bank account for deposits/ | 810414 | 810414
240 | .XXPBSA_PO_APPROVAL_REQ-for scheduling/ | 810414 | 810414
241 | .Receipt Apply/ | 810414 | 810414
242 | .Customer remaining/ | 810414 | 810414
243 | .Daily Rates/Xrigger/ | 810414 | 810414
244 | .Employee list of ERP users/ | 810414 | 810414
245 | .JSON output for successful operation response as agreed | 810414 | 810414
246 | .head office\products\supplier apis testing 3/5**** | 810414 | 810414
247 | .Inter-Stock Transfer Variation JE (SrcCr- RecDr-) and Price Adjustment\Product Movement JE | 810414 | 810414
248 | .Printer Service - SR 1/2/ | 810414 | 810414
249 | .AP invoice track asset tick based on previous asset GRN | 810414 | 810414
250 | .Outlet mapping | 810414 | 810414
251 | .credit period based on supplier brought invoice date ++ | 810414 | 810414
252 | .VAT NBT distributions api change ETA | 810414 | 810414
253 | .PO Approvals/PO Responsibility Matrix (Product Category wise approvals) | 810414 | 810414
254 | .AP Approvals amounts only/ | 810414 | 810414
255 | .Sales with Credit Sales and Settlement | 810414 | 810414
256 | .28th October clone to SLT cloud finalize later with DBA/ | 810414 | 810414
257 | .Delivery Note Format*** | 810414 | 810414
258 | .Regression Testing readiness*** | 810414 | 810414
259 | .item template for purchasing and purchase flag/ | 810414 | 810414
260 | .auto create outlet | 810414 | 810414
261 | .schedule :deliveryimport+delivery-process/ :supret-import+supret-process/ | 810414 | 810414
262 | items/ supplier/ | 810414 | 810414
263 | .rejected-lines??? | 810414 | 810414
264 | .Remittance Letter from HR asap EoD | 810414 | 810414
265 | .request admin rights to set Oracle Report Builder TEMP folder/ | 810414 | 810414
266 | .Purchase\Purchasing Flag in item upload / | 810414 | 810414
267 | .supplier type method in supplier master - userwise invoice batch / | 810414 | 810414
268 | .VAT\NBT % from procurement / Distribution Set Created needs to upload the LSL PO data later/ | 810414 | 810414
269 | .List of Standard BI Publisher Reports available within Oracle Fusion Applications (Doc ID 1458860.1)/ | 810444 | 810444
270 | asset location default/ | 810444 | 810444
271 | .AS image attach (demo 1/2 and clear img directories before prod migration) and Cash to GL/ | 810444 | 810444
272 | .Apex_Collection/ | 810444 | 810444
273 | done-tasks | 810565 | 810626
274 | MD 50 4th week | 810565 | 810626
275 | JE and AP batches restriction\ | 810565 | 810626
276 | approval to pbsa payload\ | 810565 | 810626
277 | PR approvals from APEX UI-line level status flags for PR and SUP RET tables - Eg. no items in lorry of the supplier & rejected lines testing or reject real time scenario 3rd week | 810565 | 810626
278 | sup-ret-req->outlet->ho->approve->oracle->apex approve for request->ret approval to pbsa payload->send to outlet from ho->import summary\ | 810565 | 810626
279 | PR creation\approval\rejected lines - need testing...\ | 810565 | 810626
280 | negative PR for supplier return and PR approval X | 810565 | 810626
281 | define supplier return request set (XXPBSA_SUPPLIER_RET_PRC, XXPBSA_RETURN_TO_VENDOR)\ and SR testing\ | 810565 | 810626
282 | sales\payments developed API for AR credit trx\3rd week | 810565 | 810626
283 | JEs-till bankdepo\credit 3rd week\ | 810565 | 810626
284 | oracle alert for supplier customer term based and approval pending 2nd week\ | 810565 | 810626
285 | updation of summary data - merge like delivey summary 2nd week\ | 810565 | 810626
286 | email - product updates & supplier updates/GUID has updated from oracle confirmed by pbsa\ | 810565 | 810626
287 | supplier dff (personalize supplier based on employee), PO dff outlet\ and receiving control\ 5th week | 810565 | 810626
288 | PO detail report rdf for no data\ | 810565 | 810626
289 | Settlement email to supplier\customer\ | 810565 | 810626
290 | store testing\email notif. after hitting APEX to update\add flex field value set\ included in Tech. Ref Manual 5th week | 810565 | 810626
291 | reports - grns\po\ 5th week | 810565 | 810626
292 | gl posting from plsql\7th week | 810565 | 810626
293 | call to work on Saturday at LSL X | 810565 | 810626
294 | Item import org issue\8th week | 810565 | 810626
295 | batch name and invoice number update | 810565 | 810626
296 | payable source - invoice solution\7th week | 810565 | 810626
297 | SR report REF pbsa return note\7th week | 810565 | 810626
298 | invoice value changes notification\7th week | 810565 | 810626
299 | GRN ref. to Invoice\ - focus to line block - done with conc.\7th week | 810565 | 810626
300 | update response from sup ret and rej lines - after EMAIL not payload accepting\ | 810565 | 810626
301 | po/grn/sup-ret creation email - add a notifier-gl interface\requi excep seeded reports\ | 810565 | 810626
302 | 3. custom reports or std for reporting list\ | 810565 | 810626
303 | 4. sale pay\ ret pay testing, new GL sources categories config. 6th week & credit sales CR\ | 810565 | 810626
304 | 5. Item testing (update pkg ready but policy required-sr x) supplier testing\ 6th week | 810565 | 810626
305 | 6. po qty. tolerance (for more grns and dynamic srs - po for loop and imparatively running conc. plus recursively - inv. rank and sr proc.) po reject-> rcv cont-> auto create new with apex rejected (no non approval will take to supplier return summary and\or purchase request x)-SR EXT.REF#\8th week | 810565 | 810626
306 | date required po fixture\8th week | 810565 | 810626
307 | store IDs from current 10 and 2 child done coding(note in CHILD stores how???) installing microservices and data conversion cutover\ | 810565 | 810626
308 | write to clob\9th week | 810565 | 810626
309 | index po APEX tables\9th week | 810565 | 810626
310 | finalize supplier return\10th week | 810565 | 810626
311 | GUID case\10th week | 810565 | 810626
312 | XXPBSA_ENDPOINTS - outlet - connectivity\11th week | 810565 | 810626
313 | Sup. ret. weighted avg confirmation/ | 810626 | 810626
314 | partial grn from same po/ | 810626 | 810626
315 | ap invoice batch testing/ | 810626 | 810626
316 | sequence+with outletid in sales\pay/-db sequence used | 810626 | 810626
317 | po screen - re-named column for ship to location instead of dff/ | 810626 | 810626
318 | identify warehouse -> outlet transfer from a notification sent based on the inter-stock and Hold payment till inter-stock doneX | 810626 | 810626