## Sheet1
GAP REGISTER
Client Name |  |  | LSL
Project Name: |  |  | ERP Project
Project Manager Name: |  |  | Saravana S
Job Code |  |  | 1500001
ID | Module Reference | Date Identified | Identified By | Current Status | Priority | Issue Description | Assigned To Owner | Expected Resolution Date | Escalation Required (Y/N)? | Action Steps | Actual Resolution Date | Final Resolution & Rationale
| AR | 2018-09-04 | Madura | Work In Progress | Low | webservice endpoint for customer data from Oracle EBS to PBSA POS | Sayuru | 2018-09-17 | No | PBSA/Softwatch discussing on this |  | PBSA team has given a formulae to generate the Journal Entries Manually or automataed user friendly way in future. Daily Debtors movement = (Total Sales – Total Returns) – (Total Taking – Total Return payments)
2 | AR | 2018-09-04 | Pratheenpan | Closed | Low | Proper format for bank deposit note which is done from PBSA POS so that Oracle EBS can capture it more accurately | Sayuru | 2018-09-17 | No | Receipt No.-Bank Account fomat used | 2018-10-23
3 | Custom | 2018-09-04 | Madura | Closed | Low | Custom Integration Exception Report | Sayuru | 2018-09-17 | No | Exception Report email from Oracle EBS | 2018-10-29 | exception report together with failed open interfaces will be forwarded to oracleebs@lankasathosa.org
4 | Database | 2018-09-05 | Saravana | Open | Medium | Disaster Recovery for currently implementing Oracle ERP project servers | Sayuru | 2018-10-01 | No | Oracle Enterprise Manager Module has capabilities on this or use a manual Open Source Nagios like tool has to be used
5 | Custom | 2018-09-05 | Sayuru | Work In Progress | Medium | data flush policy from intermediate database server used for daily data pulls | Sayuru | 2018-10-01 | No
6 | Custom | 2018-09-05 | Sayuru | Open | Medium | Research and Technology Development(R&TD) inputs from Sathosa\softwatch\Oracle Tech Team\PBSA (eg. Data communication security) | Sayuru | 2018-10-01 | No | data security only by whitelist IP but communication protocol can be evaded
7 | Custom | 2018-09-05 | Madura | Open | Medium | dashboard for daily data analysis | Sayuru | 2018-10-01 | No
8 | Account Payables | 17/09/18 | Umar | Closed | High | after debit memo created in AP Supplier return is approved | Sayuru | 2018-10-01 | No | AME AP approvals are defined | 2018-10-22
9 | Database | 23/09/18 | Fahad | Closed | Medium | data flush policy from APEX server (related to Oracle costing\tax etc.) | Sayuru | 2018-10-01 | No | duplicated ID 5
10 | Purchasing | 16/09/18 | Sayuru/Steven | Closed | Medium | data from outlets in old PBSA - IP addresses list required (outlets IP, HO IP after api work) | Sayuru | 2018-10-01 | No | 12 outlets provided with summary data only | 2018-10-30
11 | Inventory | 19/09/18 | Sayuru/Steven | Closed | Medium | .EBS Stores ID from CoA but PBSA POS is different. .Item Master with UoM .Initial upload of Supplier\Product GUIDs | Sayuru/Steven | 2018-10-01 | No | data dump requetsed and agreed | 2018-10-30
12 | Purchasing | 17/09/18 | Madura/Sayuru | Closed | Critical | Confirm the PO reference in PR Lines and Supplier Return Request | Sayuru | 2018-10-01 | No | data with a change in PBSA POS new version | 2018-10-12
13 | Fixed Asset | 30/10/18 | Procurement DGMs and teams | Open | Medium | Engineering & Operations Procurement to PO Dept. (Spec from FA Finance to Procurement do purchasing quality check\GRN to FA Procurement | Sathosa Finance and Procurement Teams | 2018-11-02 | No | Segreration agreed and need to communicated with Oracle ERP implementation
14 | Finance | 30/10/18 | Procurement DGMs and Managers | Open | Medium | asset supplier except to PBSA POS (supplier\item creation by Finance) | Sathosa Finance and Procurement Teams | 2018-11-02 | No | fix the responsibilities from Sathosa Finance
15 | Fixed Asset | 30/10/18 | Procurement DGMs and Managers | Open | Medium | Outlet level services from PBSA POS for asset related expenses | Sathosa Finance and Procurement Teams | 2018-12-16 | No | SKU level category and services defined and submit to Oracle PBSA integration
16 | Finance | 30/10/18 | Procurement DGMs and Managers | Open | Medium | Oracle Documentation with workflows | Sathosa Finance and Procurement Teams | 2018-11-02 | No | Oracle EBS process related user guide has to be shared
Note on A6: • ID: A unique ID number used to identify the issue in the Gap Register log.
Note on B6: Module Reference: This should include relevant module for reference
Note on C6: • Date Identified: This column should be populated with the date that the issue was identified.
Note on D6: • Entered By: This column should be populated by the name of the individual who first identified the issue.
Note on E6: • Current Status: This column should be populated with the issue's current status. o Open: The issue is currently open but has not yet been addressed. o Work In Progress: The issue is being actively worked to develop a resolution. o Closed: The issue is no longer considered an active project threat and can be closed with or without resolution. Some other potential options include: o Late: The issue resolution is not yet resolved and it is past the expected resolution date. o On Hold: The issue has been put on hold. o Combined: Two issues found to be similar have been combined.
Note on F6: • Priority: This column should be populated with the priority of the issue. Valid options include the following: High, Medium, Low. These are defined as follows: o Critical: Issue will stop project progress if not resolved. o High: Issue will likely move the project back in terms of budget or timeline, or will materially affect quality or scope. o Medium: Issue will have material effect on project, has potential to be moved to high category and/or requires significant resources to manage. o Low: Issue is expected to have a moderate effect on the project, but will require resources to address.
Note on G6: • Issue Description: This column should be populated with a description of the issue.
Note on H6: • Assigned To Owner: This column should be populated by the name of the issues owner. The individual most responsible for working towards resolving the issue.
Note on I6: • Expected Resolution Date: This column should be populated with the date that the issue is expected to be resolved.
Note on J6: • Escalation Required (Y/N): This column should be populated with “Yes” if the program/project manager feels an issue needs to be escalated and “No” if escalation is not needed to resolve the issue.
Note on K6: • Action Steps: This column should be populated with the proposed steps to address the issue. Examples include, but are not limited to, developing alternatives analysis or submitting a change request.
Note on L6: • Actual Resolution Date: This column should be populated with the date that the issue was actually resolved.
Note on M6: • Final Resolution & Rationale: This column should be populated with a description of the final resolution & rationale of the issue. The resolution may be expressed in terms of one or more of the following: schedule, scope, resources, and space. The resolution description should also include a reference to the milestones impacted.