## Schedule
Module | S.No | Description | Date | Time | Mock Run Date | Comments | Responsibility
Payables | 1 | Manual Invoice Cut Over | 2018-12-01 | 12:00 | 2018-11-08
| 2 | Supplier Masters to be uploaded | 2018-12-01 | 12:00 | 2018-11-08
| 3 | Bank Master | 2018-12-01 | 12:00 | 2018-11-08
| 4 | Reconcile Nov-18 | 2018-12-01 | 12:00 | 2018-11-08 | AP Accrual, Creditor, VAT, NBT, Bank, Prepayment
| 5 | Delta Suppliers to be uploaded (prerequisite 7) | 2018-12-01 | 12:00 | 2018-11-08
| 6 | Delta Bank Masters to be uploaded (prerequisite 7) | 2018-12-01 | 12:00 | 2018-11-08
| 7 | Check Books to be uploaded | 2018-12-01 | 12:00 | 2018-11-08
| 8 | Reconcile Nov-18 remaining balances | 2018-12-01 | 12:00 | 2018-11-08
| 9 | Open Transactions - AP Invoice | 2018-12-01 | 12:00 | 2018-11-08
| 10 | Open Transactions - AP Credit Memo/Debit Memo | 2018-12-01 | 12:00 | 2018-11-08
| 11 | Open Transactions - AP Prepayments | 2018-12-01 | 12:00 | 2018-11-08
| 12 | Manual JV to reverse Open Balance Accounting impact | 2018-12-01 | 12:00 | 2018-11-08
| 13 | Close AP Period | 2018-12-01 | 12:00 | 2018-11-08
| 14 | Payment Cut Over | 2018-12-01 | 12:00 | 2018-11-08
Receivables | 1 | Manual Invoice Cut Over | 2018-12-01 | 12:00 | 2018-11-08
| 2 | Receipt Methods to be defined, so Cashier can receipt | 2018-12-01 | 12:00 | 2018-11-08
| 3 | Reconcile Open Cash, Debtors for Oct-18 | 2018-12-01 | 12:00 | 2018-11-08
| 4 | Customer Master to be uploaded | 2018-12-01 | 12:00 | 2018-11-08
| 5 | Delta Customer to be uploaded | 2018-12-01 | 12:00 | 2018-11-08
| 6 | Reconcile Nov-18 balances | 2018-12-01 | 12:00 | 2018-11-08 | Debtor Balances etc betweeen GL and AR
| 7 | Matching Cut Over | 2018-12-01 | 12:00 | 2018-11-08
| 8 | Open Transactions - AR Invoice | 2018-12-01 | 12:00 | 2018-11-08
| 9 | Open Transactions - AR Credit Memo/Debit Memo | 2018-12-01 | 12:00 | 2018-11-08
| 10 | Open Transactions - AR Receipts | 2018-12-01 | 12:00 | 2018-11-08
| 11 | Manual JV to reverse Open Balance Accounting impact | 2018-12-01 | 12:00 | 2018-11-08
| 12 | Close AR Period in EBS R12 | 2018-12-01 | 12:00 | 2018-11-08
| 13 | Clear the Reconciled Receipts | 2018-12-01 | 12:00 | 2018-11-08
General Ledger | 1 | Chart of Account Values Mapping Upload (Trial Balance) | 2018-12-01 | 12:00 | 2018-11-08
| 2 | Uploading TB from 01-Jan-18 to Oct-18 | 2018-12-01 | 12:00 | 2018-11-08
| 3 | Uploading TB for Nov-18 | 2018-12-01 | 12:00 | 2018-11-08
| 4 | Upload Budgets | 2018-12-01 | 12:00 | 2018-11-08
| 5 | Reconcile Balances | 2018-12-01 | 12:00 | 2018-11-08
| 6 | Close GL Period | 2018-12-01 | 12:00 | 2018-11-08
Fixed Assets | 1 | New Asset Category Upload | 2018-12-01 | 12:00 | 2018-11-08
| 2 | New Asset Location Upload | 2018-12-01 | 12:00 | 2018-11-08
| 3 | Asset Master Upload | 2018-12-01 | 12:00 | 2018-11-08
| 4 | Reconcile Master Data | 2018-12-01 | 12:00 | 2018-11-08
| 5 | Capitalize AP Mass Additions based Assets | 2018-12-01 | 12:00 | 2018-11-08
| 6 | Close FA Period | 2018-12-01 | 12:00 | 2018-11-08
Purchase Orders | 1 | All GRN PO to be delivered | 2018-12-01 | 12:00 | 2018-11-08
| 2 | All Open PO (and/or PR) need to be approved | 2018-12-01 | 12:00 | 2018-11-08
| 3 | Partial Delivered PO to be cancelled or fully received | 2018-12-01 | 12:00 | 2018-11-08
| 4 | Open PO and PR to be Uploaded | 2018-12-01 | 12:00 | 2018-11-08 | PBSA POS PR Number will not be matched with Oracle for the Uploaded POs. Need to go as backlogs and maintain that set of POs separately from the integration based POs
| 5 | Reconcile AP Accrual Account | 2018-12-01 | 12:00 | 2018-11-08
| 6 | Close PO Period in EBS | 2018-12-01 | 12:00 | 2018-11-08
Inventory | 1 | Item Masters to be uploaded | 2018-12-01 | 12:00 | 2018-11-08 | PBSA POS Master Items and Item Category Master
| 2 | Openning balance of Inventory Stock related Journal Entries | 2018-12-01 | 12:00 | 2018-11-08
| 3 | Close Inventory Period | 2018-12-01 | 12:00 | 2018-11-08
Cash Management | 1 | Reconcile Bank Statements as at 30-Nov-2018 | 2018-12-01 | 12:00 | 2018-11-08
| 2 | Upload Unreconciled Bank Statement Lines | 2018-12-01 | 12:00 | 2018-11-08
| 3 | Access Removal in EBS | 2018-12-01 | 12:00 | 2018-11-08