## Status (hidden)
CRP2 Testing Status - | [7 empty] | Singapore Issue Tracking Dashboard
Process Flow | Test Lead | Sub-Process | Description | Events Planned | No. of Tests Completed | No. Passed | No Failed |  | Planned | Completed | Passed | Failed | Issues Logged | Retest? | Resolved | Backlog
[8 empty] | Total | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Total |  |  |  | 0 | 0 | 0 | 0

## Test Script-WH Procurement
Procurement Test Script
Data provided in this test script is sample data and will not match with system data. This should be replaced with actual data during test by tester.
TEST CASE ID | TEST CASE DESCRIPTION | BUSINESS PROCESS | PROCESS ID | Frequency | ACTIVITY DESCRIPTION | NAVIGATION | ROLE | TEST DATA | EXPECTED RESULTS | ISSUE
Procurement PRC:
PRC01 | Procurement Process | Purchase Order Approval |  |  | Check the Purchase Order Approval | Check whether Purchase Order approval working as per workflow through Worklist / Email / Notification | Employee
|  | Purchase Order rejection |  |  | Check the Purchase Order Rejection | Check the Purchase Order Rejection at the approval using Notification | Employee
PRC02 | Delivery Acceptance | Create Receipt/GRN |  |  | Create receipts for supplier delivery |  | Receiving Agent
|  | Return to Supplier |  |  | Return to supplier from receipt created | From the navigator icon click on Receipts | Receiving Agent
PRC03 | Review/Post Accounting | Receipt Accounting Distributions |  |  | Review Receipt Accounting Distribution | Run the process ‘Transfer Transaction from Receipt to Costing' | Cost Accountant
[6 empty] | Run the process ‘Create Receipt Accounting Distributions' | Cost Accountant
[6 empty] | Costing > Receipt Accounting > Review Receipt Accounting Distributions | Cost Accountant
|  | Create Accounting for Subledger |  |  | Run Create Accounting for Subledgers and review the journals | Run Create Accounting | Cost Accountant
[6 empty] | Select the Subledger Application as Receipt Accounting | Cost Accountant
[6 empty] | Select the Ledger - LSL Ledger | Cost Accountant
Submit
[6 empty] | To view Journal Entries | Cost Accountant
[6 empty] | Review Receipt Accounting Distribution to view entries Or view the Exception report output in schedule processes to view all the entries | Cost Accountant
|  | Cost Accounting Distributions |  |  | Review Cost Accounting Distribution | Run the process ‘Transfer Transaction from Inventory to Costing' | Cost Accountant
[6 empty] | Run the process ‘Create Cost Accounting Distributions' | Cost Accountant
[6 empty] | Costing > Cost Accounting > Review Cost Accounting Distributions | Cost Accountant
|  | Create Accounting for Subledger |  |  | Run Create Accounting for Subledgers and review the journals | Run Create Accounting | Cost Accountant
[6 empty] | Select the Subledger Application as Cost Accounting | Cost Accountant
[6 empty] | Select the Ledger - LSL Ledger | Cost Accountant
Submit
[6 empty] | To view Journal Entries | Cost Accountant
[6 empty] | Review Cost Accounting Distribution to view entries Or view the Exception report output in schedule processes to view all the entries | Cost Accountant

## Test Script-InternalRequisition
Procurement Test Script
Data provided in this test script is sample data and will not match with system data. This should be replaced with actual data during test by tester.
TEST CASE ID | TEST CASE DESCRIPTION | BUSINESS PROCESS | PROCESS ID | Frequency | ACTIVITY DESCRIPTION | NAVIGATION | ROLE | TEST DATA | EXPECTED RESULTS | ISSUE
Internal Requisition PRC:
PRC06 | Internal Requisition Process | Create Internal Requisition using Master Items | PRC06.1 |  | Create Internal Requisition (IR) to request items to the Branch/ Department | Home > Procurement > Requisitions > More Task > Enter Requisition Line | Advance Procurement Requester
[6 empty] | Search item using search option (i.e. magnifying glass icon in the corner of the item field) | Advance Procurement Requester
[6 empty] | Enter the desired quantity in Quantity field | Advance Procurement Requester
[6 empty] | Request Reason: New Item or Replacement (This is mandatory) | Advance Procurement Requester
|  | Review Requisition details | PRC06.2 |  | Requester details update | Select a different requester | Advance Procurement Requester
|  |  | PRC06.3 |  | Requested Delivery Date | Update the required delivery date | Advance Procurement Requester
|  |  | PRC06.4 |  | Charge account generation | Check the default charge account | Advance Procurement Requester
|  |  | PRC06.5 |  | Enter the Cost Center details, if required to charge the cost directly to a specific cost center/ department | Click on the icon next to charge account field to view segments in the charge account | Advance Procurement Requester
[6 empty] | Click on the dropdown list in Cost Center segment | Advance Procurement Requester
[6 empty] | Search the Cost Center/ Department | Advance Procurement Requester
[6 empty] | Click 'Ok' | Advance Procurement Requester
|  |  | PRC06.6 |  | Delivery to location | Check the deliver location and if required change the location | Advance Procurement Requester
|  |  | PRC06.7 |  | Select the relevant Source Org | Select particular source org using select source option (ADMIN, CONSUMABLES, IT, MARKETING and VEHICLE) | Advance Procurement Requester
[6 empty] | Click on Add to Cart | Advance Procurement Requester
|  |  | PRC06.8 |  | Create Requisition with multiple lines | To create an IR with multiple lines, follow the above steps from PRC06.1 to PRC06.7 | Advance Procurement Requester
|  |  | PRC06.9 |  | Review the cart | Review or Submit for Approval | Advance Procurement Requester
|  |  | PRC06.10 |  | Requisition PDF document view | If reviewed, Click on View PDF to check the output | Advance Procurement Requester
|  |  | PRC06.11 |  | Query the Requisition | Home > Procurement > Requisitions > Manage Requisitions | Advance Procurement Requester
[6 empty] | Search the Requisition number | Advance Procurement Requester
|  |  | PRC06.12 |  | Copy the Internal Requisition | Home > Procurement > Requisitions | Advance Procurement Requester
[6 empty] | Go to Manage Requisitions | Advance Procurement Requester
[6 empty] | Select the requisition line which need to be duplicated | Advance Procurement Requester
[6 empty] | Actions > Duplicate | Advance Procurement Requester
[6 empty] | Requisition is being duplicated with a new IR number | Advance Procurement Requester
|  |  | PRC02.13 |  | Edit Requisition | Home > Procurement > Requisitions > Manage Requisitions | Advance Procurement Requester
[6 empty] | Search the Requisition number | Advance Procurement Requester
[6 empty] | Click on Requisition Number | Advance Procurement Requester
[6 empty] | Click on Actions > Edit Order | Advance Procurement Requester
[6 empty] | Make required change in Transfer Order and Submit (You can only reduce the quantity) | Advance Procurement Requester
PRC07 | Review and Approve Requisitions | Submit created requisition for approval | PRC07.1 |  | Create requisition and submit for approval | Home > Procurement > Requisitions | Employee
[6 empty] | See in Manage Requisitions | Employee
[6 empty] | Click on Requisition > Edit > Submit | Employee
|  | First level approval | PRC07.2 |  | Check the first level Branch/ Department approval | Login as Approver | Employee
[6 empty] | Click on Notification Bell | Employee
[6 empty] | Click on the Notification link | Employee
[6 empty] | Use the Approve Option | Employee
[5 empty] | Request for More Information | Actions > Request for More Information | Employee
[6 empty] | Submit | Employee
|  | Reject Requisition with comments | PRC07.3 |  | Reject Requisition with comments | Login as Approver | Employee
[6 empty] | Click on Notification Bell | Employee
[6 empty] | Click on the Notification link | Employee
[6 empty] | Click on Reject and Enter Comments in Notification | Employee
|  | Second level approval | PRC07.4 |  | Check the second level Line Manager approvals | Login as Approver | Employee
[6 empty] | Click on Notification Bell | Employee
[6 empty] | Click on the Notification link | Employee
[6 empty] | Use the Approve or Reject Option | Employee
PRC08 | Item Issuing Process | Check New Internal Requests | PRC08.1 |  | View/ Edit new internal requisitions by Process Center | Inventory Management > View BY | Inventory Manager
[6 empty] | Select the preferred Inventory Org | Inventory Manager
[6 empty] | Click on Apply | Inventory Manager
[5 empty] | View Transfer Orders | Tasks (Inventory) > Manage Transfer Orders | Inventory Manager
[6 empty] | Select preferred Source Organization from LOV | Inventory Manager
[6 empty] | Search | Inventory Manager
[6 empty] | Note down Transfer Order (TO) number | Inventory Manager
[6 empty] | If need to view the TO click on the TO number | Inventory Manager
[5 empty] | Edit Transfer Orders (Edit Requested Quantity | Reduce requested quantity, if required Note: You cannot increase the quantity | Inventory Manager
[6 empty] | Submit | Inventory Manager
|  | Pick Confirmation | PRC08.2 |  | Pick consumable item to be issued | Show Task: Picks > Confirm Pick Slip | Inventory Manager
[6 empty] | Search by TO number | Inventory Manager
[6 empty] | Click on pick slip number | Inventory Manager
[6 empty] | Enter pick quantity | Inventory Manager
[6 empty] | Confirm | Inventory Manager
[5 empty] | Pick fixed asset item to be issued | Follow the above steps as in PRC08.2 (Do not confirm yet) | Inventory Manager
[6 empty] | Select serial number from LOV | Inventory Manager
[6 empty] | Confirm | Inventory Manager
|  | Ship Confirmation | PRC08.3 |  | Ship items from warehouse to the requested location | Inventory Management > Show Tasks (Shipments) > Manage Shipments | Warehouse Operator
[6 empty] | Enter Ship-from Organization (ADMIN / CONSUMABLES / IT / MARKETING / VEHICLE) | Warehouse Operator
[6 empty] | Select 'Ready to Ship' in Shipment Status LOV | Warehouse Operator
[6 empty] | Select the Line Item and Click on shipment number | Warehouse Operator
[6 empty] | Click on 'Inventory Details' tab in Lines area to check quantity, serial number details | Warehouse Operator
[6 empty] | Click on ship confirm | Warehouse Operator
[6 empty] | Warning message will appear | Warehouse Operator
[6 empty] | Click 'Yes' | Warehouse Operator
PRC09 | Delivery Acceptance | Receive & Acknowledge delivered items | PRC09.1 |  | Create a receipt for a consumable item | Home > Procurement > My Receipts | Advance Procurement Requester
[6 empty] | Select Item dues as Any time & Select the Requisition BU | Advance Procurement Requester
Search by Requisition number
[6 empty] | Click on Search | Advance Procurement Requester
[6 empty] | Select the Line and Click on Receive | Advance Procurement Requester
[6 empty] | Enter the Quantity and click on Submit | Advance Procurement Requester
[6 empty] | Popup notification will show the Receipt number | Advance Procurement Requester
|  | Receipt/GRN correction | PRC09.2 |  | Correction on the created Receipt | Home > Procurement > My Receipts > Task menu > Manage Receipts | Receiving Agent
[6 empty] | Search from Receipt number to be corrected | Receiving Agent
[6 empty] | Select the line to be corrected and click on correct button | Receiving Agent
[6 empty] | Select the Correction line again and do the correction for Receipted quantity | Receiving Agent
[6 empty] | Enter the quantity and click on submit button | Receiving Agent
|  | Return to Warehouse | PRC09.3 |  | Return to Warehouse from Created Receipt | Home > Procurement > My Receipts > Task menu > Manage Receipts | Receiving Agent
[6 empty] | Search from Receipt number to be returned | Receiving Agent
[6 empty] | Select the receipt line to be returned and click on Return button | Receiving Agent
[6 empty] | Enter the quantity to be returned | Receiving Agent
[6 empty] | Select the reason | Receiving Agent
[6 empty] | Click on Submit button | Receiving Agent
|  | Create Receipt /GRN on behalf of another requester (Internal Requisition) | PRC09.4 |  | Create a receipt for a fixed asset item | Go to Inventory Management | Receiving Agent
[6 empty] | Click on 'View By' to select preferred Inventory Org | Receiving Agent
[6 empty] | Select the organization as BRANCH from LOV and click on Apply button (This step need to be followed for Branch FA acknowledgements) | Receiving Agent
[6 empty] | Show Tasks: Receipt > Receive Expected Shipments | Receiving Agent
[6 empty] | Search receipt by TO number | Receiving Agent
[6 empty] | Select the line to be received and click on 'Receive' button | Receiving Agent
[6 empty] | Enter the quantity received | Receiving Agent
[6 empty] | Click on create receipt button | Receiving Agent
[6 empty] | Click on Submit button | Receiving Agent
PRC10 | Review/Post Accounting | Cost Accounting Distributions | PRC10.1 |  | Review Cost Accounting Distribution | Run the process ‘Transfer Transaction from Inventory to Costing' | Cost Accountant
[6 empty] | Run the process ‘Create Cost Accounting Distributions' | Cost Accountant
[6 empty] | Costing > Cost Accounting > Review Cost Accounting Distributions | Cost Accountant
|  | Create Accounting for Subledger | PRC10.2 |  | Run Create Accounting for Subledgers and review the journals | Run Create Accounting | Cost Accountant
[6 empty] | Select the Subledger Application as Cost Accounting | Cost Accountant
[6 empty] | Select the Ledger - LBF_Ledger | Cost Accountant
[6 empty] | Submit | Cost Accountant
[6 empty] | To view Journal Entries | Cost Accountant
[6 empty] | Review Cost Accounting Distribution to view entries Or view the Exception report output in schedule processes to view all the entries | Cost Accountant
|  | Receipt Accounting Distributions | PRC10.3 |  | Review Receipt Accounting Distribution | Run the process ‘Transfer Transaction from Receipt to Costing' | Cost Accountant
[6 empty] | Run the process ‘Create Receipt Accounting Distributions' | Cost Accountant
[6 empty] | Costing > Receipt Accounting > Review Receipt Accounting Distributions | Cost Accountant
|  | Create Accounting for Subledger | PRC10.4 |  | Run Create Accounting for Subledgers and review the journals | Run Create Accounting | Cost Accountant
[6 empty] | Select the Subledger Application as Receipt Accounting | Cost Accountant
[6 empty] | Select the Ledger - LBF_Ledger | Cost Accountant
Submit
[6 empty] | To view Journal Entries | Cost Accountant
[6 empty] | Review Receipt Accounting Distribution to view entries Or view the Exception report output in schedule processes to view all the entries | Cost Accountant

## Test Script-Inventory
Inventory Test Script
Data provided in this test script is sample data and will not match with system data. This should be replaced with actual data during test by tester.
TEST CASE ID | TEST CASE DESCRIPTION | BUSINESS PROCESS | PROCESS ID | ACTIVITY DESCRIPTION | NAVIGATION | ROLE | TEST DATA | EXPECTED RESULTS | ISSUE
Inventory INV:
INV01 | Preferred Inventory Organization | Select Preferred Inventory Org | INV01.1 | Select the User Preferred Inventory Org in Inventory Module | Go to Inventory Management | Inventory Manager
[5 empty] | Change the preferred Inventory Org prior to perform any task | Inventory Manager
[5 empty] | Go to 'View By' in the top right corner of UI | Inventory Manager
[5 empty] | Select preferred Inventory Org from LOV | Inventory Manager
[5 empty] | Apply | Inventory Manager
INV02 | On-Hand Quantity | View On-Hand Quantity | INV02.1 | Check on-hand quantity of an item in Inventory Org / Subinventory levels | Inventory Management > Task: Inventory > Manage Item Quantities | Inventory Manager
[5 empty] | Enter the item in search field and Click on Search | Inventory Manager
[5 empty] | Click on the arrow to view the quantity at Inventory Org level and Subinventory | Inventory Manager
[5 empty] | Click 'Done' to exit the window | Inventory Manager
| Review Item movement | Review Item Supply and Demand | INV02.2 | Review supply and demand of an item (Item Movement) | Inventory Management > Task: Inventory > Review Item Supply and Demand | Inventory Manager
[5 empty] | Search by item and the relevant Inventory Org | Inventory Manager
[5 empty] | Details can be viewed such as 'As at date on-hand quantity, item movement based on document number' | Inventory Manager
INV03 | Review Completed Transactions | Review Completed Transactions | INV03.1 | Review all types of completed transactions | Inventory Management > Task: Inventory > Review Completed Transactions | Inventory Manager
[5 empty] | Search by required details; Organization: Preferred Inventory Org Either 'Item or Transaction Date' can be given can be given as search criteria | Inventory Manager
[5 empty] | Search | Inventory Manager
[5 empty] | All the transactions, based on parameters given will appear in UI | Inventory Manager
INV04 | Material Requests | Issue out items without a request | INV04.1 | Issue out items to a expense destination without a request | Inventory Management > Show Tasks: Inventory > Manage Material Requests | Inventory Manager
[5 empty] | Click on ' + ' sign to add a new line | Inventory Manager
[5 empty] | System generated movement request number will be available | Inventory Manager
[5 empty] | Transaction Type: Movement Request Issue (This will expense the issued goods) | Inventory Manager
[5 empty] | Destination Account: enter relevant charge account | Inventory Manager
|  |  | INV04.2 | Add multiple lines | Add Line, Click on + sign | Inventory Manager
[5 empty] | Select the item that need to be issued | Inventory Manager
[5 empty] | Enter quantity | Inventory Manager
[5 empty] | Add (+) multiple lines as above | Inventory Manager
[5 empty] | Save | Inventory Manager
[5 empty] | Submit | Inventory Manager
[5 empty] | Notification will appear for successfully created transactions | Inventory Manager
INV05 | Miscellaneous Transactions | Create miscellaneous Receipt | INV05.1 | Create miscellaneous Receipt | Inventory Management > Task: Inventory > Manage Miscellaneous Transactions | Inventory Manager
[5 empty] | Type: Miscellaneous Receipt | Inventory Manager
[5 empty] | Account: Give the account | Inventory Manager
[5 empty] | Use Current Item Cost: Yes | Inventory Manager
[5 empty] | Under Lines region click on + icon to add a line | Inventory Manager
[5 empty] | Select item (Use magnifying glass to search item by description) | Inventory Manager
[5 empty] | Select the Subinventory | Inventory Manager
[5 empty] | Enter the Quantity | Inventory Manager
|  |  |  | Add multiple lines | Under Lines region click on + icon to add another line | Inventory Manager
[5 empty] | Submit | Inventory Manager
[5 empty] | Click OK in Confirmation message | Inventory Manager
|  | Create miscellaneous Issue | INV05.2 | Create miscellaneous Issue | Inventory Management > Task: Inventory > Manage Miscellaneous Transactions | Inventory Manager
[5 empty] | Account: Give destination account | Inventory Manager
[5 empty] | Use Current Item Cost: Yes | Inventory Manager
[5 empty] | If 'Use Current Item Cost: No' Manually enter the cost using ‘Enter Cost’ option in line level | Inventory Manager
[5 empty] | Add transaction line | Inventory Manager
[5 empty] | Select item (Use magnifying glass to search item by description) | Inventory Manager
[5 empty] | Select the Subinventory | Inventory Manager
[5 empty] | Enter the Quantity | Inventory Manager
|  |  |  | Add multiple lines | Under Lines region click on + icon to add another line | Inventory Manager
[5 empty] | Submit | Inventory Manager
[5 empty] | Click OK in the pop-up notification | Inventory Manager
INV06 | Subinventory Transfer | Create Subinventory Transfer | INV06.1 | Transfer item quantities from one subinventory to another subinventory within the same inventory Org | Inventory Management > Tasks: Inventory > Manage Subinventory Transfer | Inventory Manager
[5 empty] | Select Type: Subinventory Transfer | Inventory Manager
[5 empty] | Add transaction line | Inventory Manager
[5 empty] | Select item (Use magnifying glass to search item by description) | Inventory Manager
[5 empty] | Select source subinventory where the item is currently available | Inventory Manager
[5 empty] | Select destination subinventory where the item need to be transferred to | Inventory Manager
[5 empty] | Quantity: Enter quantity to be transferred | Inventory Manager
|  |  |  | Add multiple lines | Under Lines region click on + icon to add a line | Inventory Manager
[5 empty] | Submit | Inventory Manager
[5 empty] | Click OK in the pop-up notification | Inventory Manager
INV07 | Physical Inventory Count | Select Preferred Inventory Org | INV07.1 | Select the User Preferred Inventory Org in Inventory Module | Follow the steps as in INV01 to select the Inventory Org
|  | Manage Physical Inventories | INV07.2 |  | Inventory Management > Show Tasks: Counts > Manage Physical Inventory
|  | Create physical inventory template | INV07.3 | Create a template for Physical Inventory Count | Enter template name
Dynamics Tags Allowed - Check
Sub inventories – All
Approval type: Always
Tag Type: Default
Enter starting default tag number
Save & Close
|  | Generate Physical Inventory Snapshot | INV07.4 | Take snapshot of all the items in selected Inventory Org | Manage Physical Inventory > Search template you created in the 'Name' field
Select the template (Click on the line with the template you created)
Actions > Generate Physical Inventory Snapshot
|  | Generate Physical Inventory Tags | INV07.5 | Create Unique Tag number for each item in the selected Org | Manage Physical Inventory > Search template you created in the 'Name' field
Select the template (Click on the line with the template you created)
Actions > Generate Physical Inventory Tags
Notification will appear with Process ID, Click OK
|  | Print Physical Inventory Tag Listing Report | INV07.6 | Run the Program Print Physical Inventory Tag Listing Report | Navigator > Tools > Schedule Processes
Click on Schedule New Process button
Search 'Print Physical Inventory Tag Listing Report'
Organization: Select the preferred Inventory Org
Physical Inventory: Choose the Physical Inventory Template you created
Click on 'Submit'
Click 'OK'
|  |  |  | View Physical Inventory Tag List Report | There are two options to view the output;
Option 1: Select Line > Output > Default Document (A web form will be opened)
Option 2:Select Line > Output > Republish (This option enable users to get output format in PDF, Excel and etc.)
Actions > Exports > PDF / Excel
|  | Record Physical Inventory Tags | INV07.7 | Update physical count results to the system | Inventory Management > Show Tasks: Counts > Record Physical Inventory Tags
Record the physical count in the 'Count Quantity' field for each item
Click on 'Save & Close'
|  | Approve Physical Inventory Adjustments | INV07.8 | Approve physical count results to adjust item quantities with variance | Login as Approver | Inventory Manager
[5 empty] | Go to Inventory Management > Show Tasks: Counts > Physical Inventory > Approve Physical Inventory Adjustments | Inventory Manager
[5 empty] | Search by Physical Inventory Template name in the search field | Inventory Manager
[5 empty] | Select the template (Click on the line with the template that needs approval) | Inventory Manager
[5 empty] | Choose item line (Physical count, system balance and the variance in quantity and value are available to view) | Inventory Manager
[5 empty] | Change the adjustment status | Inventory Manager
|  |  |  | Approve | If status changed to ‘approved, the variances will auto adjusted | Inventory Manager
|  |  |  | Reject | If status changed to ‘rejected, the variances will not be adjusted in the system | Inventory Manager
|  |  |  | Pending | If the status is pending, approver has the privilege to view and take action later (i.e. either to approve or reject) | Inventory Manager
Select your mane from LOV in Reviewer field
[5 empty] | Click on 'Save & Close' | Inventory Manager
|  | Post Physical Inventory Adjustments | INV07.9 | Post adjustment entries for the approved variances | Manage Physical Inventories > Select Template > Actions > Post Physical Inventory Adjustment | Inventory Manager
[5 empty] | Enter Adjustment date | Inventory Manager
[5 empty] | Click ‘Ok’ | Inventory Manager
[5 empty] | Click OK in the pop-up notification | Inventory Manager

## Definitions (hidden)
Term | Description
Upstream Tests | Testcases that must be completed BEFORE the current testcase can be run. Use Test case IDs
Downstream Tests | Testcases that cannot be started until the current testcase is completed. Use Test case IDs
Planned Start Date | Date when the current testcase is planned to start. Once the Test Execution starts, this date cannot be changed
Planned End Date | Date when the current testcase is planned to complete. Once the Test Execution starts, this date cannot be changed
Role Assigned | Can be system roles or permissions granted as part of SDLC