## Business User Test Script
FA Test Script |  |  | FA Test Script
Data provided in this test script is sample data and will not match with system data.This should be replaced with actual data during test by tester. |  |  | Data provided in this test script is sample data and will not match with system data.This should be replaced with actual data during test by tester.
TEST CASE ID | TEST CASE DESCRIPTION | BUSINESS PROCESS | ACTIVITY ID | ACTIVITY DESCRIPTION | NAVIGATION | EXPECTED RESULT | ISSUE
FIN-FA:
FA01 | Manually Create Asset Record | Add asset via manual addition | FA01.1 | Add asset via manual addition | Navigator > Fixed Assets > Assets
Select the Task >Add Asset
Select Asset Book
Select Asset Type "Capitalized"
Search and Select Category
Enter Information and click 'Next
Edit Depreciation Expence Account and Location if needed, then fill out all other necessary information and click "Submit"
FA02 | Asset addition through spreadsheet | Add assets via a Spreadsheet | FA02.1 | Add assets via an excel sheet | Navigator > Fixed Assets > Assets
Select the Task>Add assets in spreadsheet
Enter the following mandatory fields- Book Name & Asset Type
Click Go
*Download the excel file and login using your username and password.
Enter the Mandatory fields on the excel template(Interface Line no.,Asset Type,Description,Category,Date placed in service,Cost,Location,Depreciation Expense a/c
Enter the Barcode no. in the Serial No. column
Change the Queue Name to "Post"
Click Submit button to run the Prepare Mass Additions Program.
Click Post to run the Post Mass Additions Program
FA03 | Mass Additions | Addition of Multiple assets pushed from Payables invoice lines | FA03.1 |  | Select Additions infoltile>Incomplete
Select Prepare all button
Change the Queue Name to "Post"
Enter the date placed in service,Location,Depreciation Expense account
Click Submit button to run the Prepare Mass Additions Program.
Click Post to run the Post Mass Additions Program
| Addion of a Single asset from Mass Additions | Addition of a single asset from a invoice line | FA03.2 |  | Select Additions infoltile>Incomplete
Select the line which represents the relevant invoice number.
Actions > Edit to enter any missing information such as category, location, Depreciation Expense a/c,tag number, serial number and etc.
Change the queue status to “POST” and click “Save And Close”.
Proceed to “Read to Post” heading under Additions infotile. (It will represent all the lines with queue status with “POST”.
Select the line which represents the relevant invoice number.
Click “Post All” to run “Post Mass Additions ‘’ Program.
FA04 | Asset Split | Splitting a single invoice line with multiple units to several lines | FA04.1 |  | Navigator > Fixed Assets > Assets
Select the inovice line which you need to split into single units
Click "Yes"
FA05 | Add to Asset | Adding assets to a capitalized asset | FA05.1 |  | Navigator > Fixed Assets > Assets
Select "Add to Asset" button
Search the asset you need to add with another asset
Click "Preview Add to Asset" button & Enable Amortize check box
Select Add to Asset button
FA06 | Manually Create Asset Record-CIP Asset Addition | Add asset, type CIP | FA06.1 | Add asset, type CIP | Navigator > Fixed Assets > Additions
Select Task > Add Asset
Select Asset Book
Select Asset Type "CIP"
Search and Select Category
Enter Information and click 'Next
Click Submit
FA07 | Capitalize CIP into asset | Capitalise CIP into asset | FA07.1 | Capitalise CIP into asset | Navigator > Fixed Assets > Assets
Select Task >Capitalize CIP Assets
Select Asset Book and Asset Type as "CIP" and click 'Search'
Select CIP Asset and click 'Capitalise'
Enter Date Placed in Service and click 'OK'
FA08 | Change Financial details of the asset | Asset Adjustment | FA08.1 | Asset Adjustment | Navigator > Fixed Assets > Assets
Select Task >Adjust Asset
Query the asset required > Change financial details
Perform the relevant change required for the asset and submit.
| Asset Category Change | Changing Categories | FA08.2 | Changing Categories | Navigator > Fixed Assets > Assets
Select Task "Adjust Asset"
Query the asset required > Change Category
Enter the new category > Click Submit
FA09 | Perform Asset retirement | Asset retirement | FA09.1 | Asset retirement - Partial Retirement | Navigator > Fixed Assets > Assets
Select Task >Retire Assets
Select Asset Book
Query Asset
Click Search
Choose the asset
Select 'Action' > 'Retire Cost' / 'Retire Units'
In Retirement detail, Insert value less than orignial cost of that asset
Enter other Information
Click 'Submit'
|  | Asset retirement | FA09.2 | Asset retirement - Full Cost Retirement | Navigator > Fixed Assets > Assets
Select Task >Retire Assets
Select Asset Book
Query Asset
Click Search
Choose the asset
Select 'Action' > 'Retire Cost' / 'Retire Units'
In Retirement detail, Insert the orignial cost of that asset
Enter other Information
Click 'Submit'
|  |  | FA09.3 | Ready to post Asset | In Asset Dashboard retirement box, there is one asset as ready to post
Select that asset and click post
|  |  | FA09.04 | Asset retirement - mass retirement | Navigator > Fixed Assets > Retirements
Select the Task 'Manage Mass Retirements'
Click New button
Enter Information
Click 'Next'
Enter Information
Click 'Submit'
Navigator > Fixed Assets > Retirements
Click 'Prepare in Spreadsheet' under 'Pending Mass Retirements'
Open Spreadsheet
Click 'Yes'
Connect to Instance
Update Spreadsheet
Click 'Save and Post Transaction'
FA10 | Perform Asset Reinstatement | Asset Reinstatement | FA10.01 | Asset Reinstatement | Navigator > Fixed Assets > Assets
Select the Task 'Reinstate Assets'
Select Asset Book
Fill in Asset details
Click 'Search'
Select Asset
Click 'Reinstate'
|  |  | FA10.02 | Ready to post Asset | In Asset Dashboard retirement box, there is one asset as ready to post
Select that asset and click post
FA11 | Transfer asset | Transfer Asset from one location to another and update the assignment | FA11.01 | Transfer Asset from one location to another and update the assignment | Navigator > Fixed Assets > Assets
Select Task >Transfer Assets'
Select Asset Book, Asset Type as "Capitalized", Description and Asset Number
Click 'Search'
Select Asset
Click 'Transfer Asset'
Enter Information including tranfer date
Click 'Submit'
Click' Done'
FA12 | Asset Adjustment - mass Adjustment ADFDI/Using Spreadsheet | Asset reclassification - mass reclassification ADFDI | FA12.01 | Asset reclassification - mass reclassification ADFDI | Navigator > Fixed Assets > Assets
Select Task >Adjust assets in spreadsheet
Select Asset Book
Select Transaction Type as "Change Category"
Click 'Next'
Enter Information
Click 'Submit'
Navigator > Fixed Assets > Financial Transactions
Select the Mass Transaction Submitted
Click 'Prepare in Spreadsheet'
Open Spreadsheet
Verify information / Update if required
Click 'Save and Post Transactions'
|  | Mass Transfer | FA12.02 | Asset transfer - mass transfer ADFDI | Navigator > Fixed Assets > Assets
Select the Task 'Transfer Asset in Spreadsheets'
Select Asset Book
Click 'Next'
Enter Information
Click 'Submit'
|  |  | FA12.03 | Asset reclassification - With Amortize checkbox | Navigator > Fixed Assets >Assets
Select the Task 'Adjust Assets'
Select Asset Book
Fill in Asset details
Click 'Search'
Select Asset
Select 'Action' > 'Change Financial Details'
Select Amortize check box and Amortization start date
Fill other information and Submit
FA13 | Intercompany Transfer of Assets-Sale of Assets | Intercompany sales of asset | FA13.01 | Asset retirement - manual | Navigator > Fixed Assets > Retirements
Select the Task >Retire Assets
Select Asset Book
Query Asset
Click Search
Choose the asset
Select 'Action' > 'Retire Cost' / 'Retire Units'
Enter Information including the sales details
Click 'Submit'
FA14 | Perform Asset Impairment | Perform Asset Impairment | FA14.01 | Perform Asset Impairment | Tools>Impair Assets
Select the Asset Book and select Next
Select ‘Book’ and click ‘Search’
Enter the information and click ‘Save and Submit’. Note: 1. When there is ‘***’ sign, it indicates that you only need to put either one of the information. 2. Impairment Status: You can choose between ‘New’ or ‘Preview’. If you choose ‘New’, once uploaded, you will need to requery the batch and choose Action > Edit to download again and change the status to ‘Preview’. If you choose ‘Preview’, you can post the impairment transaction once it is uploaded.
Once uploaded, go to Tools > Scheduled Process to review the Impairment report. “ “Asset Impairment Report”
Select the impairment batch and click ‘Post’
FA15 | Run Depreciation | Calculating Depreciation | FA15.01 |  | Navigator> Fixed Assets> Assets
Select Depreciation Infotile>Click the drop down arrow
Click Calculate Depreciation button
|  |  | FA15.02 | Period Close | Under calculate depreciation button there is an option to select Period Close
FA16 | Asset Revaluation | Revaluation of Assets | FA16.01 | Revaluation of Assets | Navigator> Fixed Assets> Assets
Tasks> Revalue assets
Click on the Add icon.
Select the required book to create revaluation and Click Next.
- Enter a transaction group
- Enter the method (Cost/ NBV)
- Enter the transaction date
Under the asset selection criteria, User can enter
- The asset numbers he wishes to revalue
- Or provide the date placed in service ranges
Under the revaluation rules, enter the revaluation method
Click Submit.
|  |  | FA16.02 | Prepare And Post | Search from the Transaction Group
Click Prepare All.
“Manage Revaluation” Excel sheet would get downloaded
Login to the system using your username and password.
Verify the information you have provided and change posting status to “Post
Enter a value for either Percent, Amount, or Fair Value
Click on Submit.
FA17 | Peform What-If Analysis |  | FA17.01 |  | Navigator> Fixed Assets> Assets
Tasks>Perform What-If Analysis
Fill the following mandatory fields
- Enter the asset book
- Provide the starting period
- Currency
- Number of periods.
Under the asset selection, provide the details of the asset which you wish to analyze.
Under the depreciation scenario, provide the method user wish to see the depreciation to occur for the assets.
Click Submit.
|  |  | FA17.02 | Run What-if Analysis Report | Navigator > Tools > Scheduled Processes > Schedule New Process
Click 'Search'
Select "What-if Analysis Report"
Enter the report parameters
Click 'Submit'
Click on the default document
FA18 | Mass Copy | Copying Corporate asset book details to the Tax Books |  |  | Navigator> Fixed Assets> Assets
Tools>Manage All Books
Select the Tax Book
Click Copy from Corporate
Select the Period
Click Submit
FA19 | Asset Inquiry | Inquirying capitalized assets |  |  | Navigator> Fixed Assets> Asset Inquiry

## Master User Test Script
FA Test Script |  |  | FA Test Script
Data provided in this test script is sample data and will not match with system data.This should be replaced with actual data during test by tester. |  |  | Data provided in this test script is sample data and will not match with system data.This should be replaced with actual data during test by tester.
TEST CASE ID | TEST CASE DESCRIPTION | BUSINESS PROCESS | ACTIVITY ID | ACTIVITY DESCRIPTION | NAVIGATION | EXPECTED RESULT | ISSUE
FIN-FA:
FA01 | Add Asset Category |  | FA01.1 | Group assets by financial information and Depriciation rules | Navigation>Setup and Maintenance | Able to proceed
[5 empty] | Go to Manage Fixed Assets Flexfield Value Sets | Able to proceed
Serach Module>Assets
[5 empty] | Select the value set code as FA_Major,FA_Minor or FA_Subminor | Able to proceed
[5 empty] | Clicks Manage values | Able to proceed
[5 empty] | Create New Major,Minor or subminor Asset Category | Able to proceed
Able to proceed
[5 empty] | Go to Manage Asset Categories | Able to proceed
[5 empty] | Click add row button and select major and minor category | Able to proceed
[5 empty] | Select all other options and save | Able to proceed
FA02 | Add Asset Locations |  | FA 02.01 | Group and Track assets by physical location | Navigation>Setup and Maintanence | Able to proceed
[5 empty] | Go to Manage Fixed Assets Flexfield Value Sets | Able to proceed
[5 empty] | Select the value set code | Able to proceed
[5 empty] | Clicks Manage values | Able to proceed
[5 empty] | Create New Location | Able to proceed
[5 empty] | Go to Manage Asset Location | Able to proceed
[5 empty] | Click add row button and add new asset location | Able to proceed
[5 empty] | Enable the asset location | Able to proceed