## Business User Test Script
AP Test Script
Data provided in this test script is sample data and will not match with system data.This should be replaced with actual data during test by tester.
TEST CASE ID | TEST CASE DESCRIPTION | BUSINESS PROCESS | ACTIVITY ID | ACTIVITY DESCRIPTION | NAVIGATION | ROLE | TEST DATA | EXPECTED RESULT | ISSUE
FIN-AP:
AP01 | Supplier Creation | Import suppliers | AP01.1 | Import suppliers to Oracle Cloud through the interface | Procurement > Suppliers > Manage Suppliers
Add Fileds - Business Relationship and Create Source
Busness Relationship - Prospective, Create Source -Web Source
Search
Verify the imported supplier details (VAT/SVAT, TIN, NBT No., Contact Details, BR No., Registered date, Address, Related party personnel)
On Edit Supplier window change Business Relationship to Spend Authorized
On Promoe to Spend Authorized window, put a justification and tick on procument BU to crate sites > Submit
Go to Sites tab > Edit Sites > Invoicing tab > Click Payment Terms drill down > Select a required payment term
Go to Site Assignments tab > Select a relevant Ship-to-Location
Enter or Edit other supplier details as per the requirement > Save and Close
AP02 | Thrid-party payments | Adding thrid-party to a supplier | AP02.1 | Adding third-party to a supplier | Procurement > Suppliers > Manage suppliers
Search for the relevant supplier
Go to supplier sites > Edit > On Edit Sites window go to Invoicing tab
On Thrid-Party Payment Relationship working area select " + " icon to add
Enter third-party name on Remit-to Supplier cell, address on Adress Name cell and From Date
Save and Close
AP03 | Create Standard Invoice | Create standard invoice not matched to PO | AP03.1 | Create standard invoice not matched to PO | Payable > Invoice > Create Invoice
Select BU > Select supplier > Enter Invoice Number > Invoice Amount
Select Invoice Type "Standard" > Other details as required
On Line level enter amount > Select Distribution Set(Predefined) or Distribution combination - select the relevant account
On Header Level go to Show More > Additional Information
Enter Contex Value > Processing Centre (Which are mandatory fields)
Invoice Action > Validation > Approve - Initiate
AP04 | Create Prepayment Invoice | Create Prepayment Invoice | AP04.1 | Create Prepayment Invoice | Payable > Invoice > Create Invoice
Enter relevent details according to a standard invoice
Select Type - Prepayment > Payment Term - Immediate
Enter line level accordingly
Invoice Action > Validation > Approve - Initiate
|  | Create Prepayment Invoice matched to PO | AP04.2 | Create Prepayment Invoice matched to PO | Payable > Invoice > Create Invoice
Identify PO
Enter Amount (which you are going to pay in advance)
Type - Prepayment > Payment Term - Immediate
Match invoice lines > Select Go icon
Search for the relevant PO > Tick to match the PO with the prepayment
Change the amount to the prepayment amount > Apply > OK
Enter other relevant details > Validate > Approve - Initiate > Save and Close
AP05 | Create Debit Memo | Create debit memo | AP05.1 | Create debit memo | Payable > Invoice > Create Invoice
Enter relevant invoice details according to a standard invoice
Enter invoic amount - in minus (both on header and line level)
Select Type - Debit Memo
Select relevant Distribution Set or Distribution Combination
Validate > Approve - Initiate > Save and Close
AP06 | Create Standard Invoice matched to PO and applying prepayment | Create Standard Invoice matched to PO and applying prepayment | AP06.1 | Create Standard Invoice matched to PO | Create Invoice > Identify PO > Enter details according to a standard invoice > Enter total invoice amount > Type - Standard
Match invoice lines > Select Go icon
On Search area, Uncheck the check boxes > Search PO
Tick to Match the PO > Apply > OK
|  |  | AP06.2 | Apply Prepayment | Go to Invoice Action > Apply or Unapply Prepayment
Select the relevant Prepayment > Apply > OK
Validate > Approve - Initiate > Save and Close
AP07 | Create Invoice with provisioning | Create Invoice with provisioning | AP07.1 | Create Invoice with provisioning | Create standard invoice > Go to details on line level > Select Context Value
Enter Branch > Provision Type > Provision Period > OK
Validate > Approve - Initiate > Save and Close
AP08 | Create Standard Invoice with VAT | Create Standard Invoice with VAT | AP08.1 | Create Standard Invoice with VAT | Create Invoice > View > Clolumn > View All > Go to Tax tab
Select Tax Classificstion - 15% VAT > Vallidate
Approval - Initiate > Save and Close
AP09 | Create invoice from spreadsheet | Create invoice from spreadsheet | AP09.1 | Create invoice from spreadsheet | Invoice > Create Invoice From Spreadsheet > Sign in to the application
Invoice Header Identifier
Enter the relevant details on the spreadsheet
Select the same Invoice Header Identifier number to each lines
Enter idetails on line levels accordingly
Click Status Viewer
Save and Submit Invoice Import
Enter BU > Invoice Group (if required) > Accounting Date > Submit
Payable > Invoice > Manage Invoice > Search the invoice
Select invoice > Actions > Validate > Approve - Initiate
AP10 | Create Recurring Invoices | Create Recurring Invoices | AP10.1 | Create Recurring Invoices | Payables > Invoice > Create Recurring Invoices > Sign in to the application
Enter the details to the header level (Enter total invoices amount)
Select a relevant Calendar Name
Select From - To periods
Enter single invoice amount
Enter Distribution Set or Distribution Combination
Click Status Viewer
Save and Submit Invoice Import
Enter BU > Invoice Group (if required) > Accounting Date > Submit
Payable > Invoice > Manage Invoice > Search the invoice
Select the invoice which has created for the relevant period > Actions > Validate > Approve - Initiate
AP12 | Expense Amortization | Expense Amortization | AP12.1 | Expense Amortization | Payables > Invoice > Create Invoice
Enter invoice details as a normal standard invoice
Enter the total invoices amount on header level
Enter amount on line level
Select Distribution Set or Distribution Combination
Go to View > Column > Show All > Multiperiod Accounting
Enter Start Date and End Date accordingly
Select relevant Accrual Account
Validate > Approve - Initiate > Save and Close
|  |  | AP12.2 | Monitor Process | Scheduled Processes > Schedule New Process
Search - Create Multiperiod Accounting > OK
Process Details > Enter relevant details > Submit
Click Refresh icon
Select Create Multiperiod Accounting Execution Report
AP13 | Cancel Unpaid Invoices | Cancel Unpaid Invoices | AP13.1 | Cancel Unpaid Invoices | Payables > Invoice > Manage Invoice
Search for the relevant invoice
Select the invoice > Action > Cancel Invoice > OK
AP14 | Foreign Currency Invoice | Foreign Currency Invoice | AP14.1 | Foreign Currency Invoice | Payables > Invoice > Create Invoice
Create the invoice as a standard invoice
Select the invoice currency on Amount cell
Select Show More on header level
Payment Currency - Select the required currency
Select Accounting tab
Enter other relevant details > Validate > Approve - Initiate > Save and Close
AP15 | FA invoice and create mass addtion | FA invoice and create mass addtion | AP15.1 | FA invoice and create mass addtion | Payables > Invoice > Create Invoice
Identify PO
Enter other relevant details according to a standard invoice
Match invoice lines > Select Go icon
Search PO > Tick to Match the PO > Apply > OK
Validate > Approve - Initiate > Save and Close
|  |  | 15.2 | Monitor Process | Scheduled Processes > Schedule New Process
Search - Create Accounting > OK
Process Details > Enter relevant details > Submit
Click Refresh icon
Select Create Accounting Execution Report
|  |  | 15.3 | FA Mass Addition | Tasks > Assets > Create Mass Addition
Enter relevant Accounting Date > Asset Book > Submit
|  |  | 15.4 | Monitor Process | Scheduled Processes > Click referesh icon
Select the report
AP16 | Bank, Branch, Bank Account and Payment document creation | Bank, Branch, Bank Account and Payment document creation | AP16.1 | Create Bank | Setup and Maintenance > Search Tasks “Manage Banks” > Click Manage Banks
Click “Create” icon on Manage Banks
Enter Country > Bank Name > Other fields as required
Click Create icon on Address level
Enter Country > Address lines > City > Other details as required
OK > Save and Close
|  |  | AP16.2 | Create Branch | Manage Banks > Search Bank name > Select the Bank > Click “Create Branch”
Enter Bank > Branch Name > Other fields as required
Click “Create” on Addresses level
Enter Country > Address lines > City > Other details as required
OK > Save and Close > Done
|  |  | AP16.3 | Create Bank Account | Search Tasks “Manage Bank Branches” > Select the task
Inquire the Bank > Select the bank > Click “Create Account”
Enter Account Name > Account Number > Currency > Legal Entity > Other details as required
Account Use - Tick "Payables" and "Receivables"
|  |  |  | GL Accounts - You have to maintain separate GL accounts for each bank accounts | Select Cash > Click “Account” drill down button > Select the relevant bank account > OK
Select Cash Clearing account of the particular bank account > Select Account drill down button > Select the relevant clearing account > Ok
|  |  |  | Additional Information | Tick “Active” and “Multicurrency account”
|  |  | AP16.4 | Create Payment Document | Select > Create icon
Payment Document > Paper Stock Type - Numbered Stock > Format - Seylan Bank Format
Payment Document Category - Check Payments > First and Last Available Document Number
OK
|  |  |  | Access to BU | Go to Business Unit Access tab
Select BU > Click “+” button > Select Payment Method - Check > Select Payment Document Category - Check Payments
OK
Save and Close > Done
AP17 | Payment For an Invoice | Payment For a Standard Invoice | AP17.1 | Payment For a Standard Invoice | Payables > Payments > Create Payment
Enter BU - LB Finance Head Office > Supplier or Party > Supplier Site >Payment Date > Type
Select Disbursement Bank Account > Payment Currency > Payment Method
Payment Process Profile - relevant profile > Payment Document - relevant document
Select “Add” icon on invoices to pay
Search the relevant invoice > Select the invoice > Apply > OK
Save and Close
AP18 | Payment For an Invoice | Payment For a Standard Invoice | AP18.1 | Payment For a Standard Invoice | Payables > Payments > Create Payment
Enter BU - LB Finance Head Office > Supplier or Party > Supplier Site >Payment Date > Type
Select Disbursement Bank Account > Payment Currency > Payment Method
Payment Process Profile - relevant profile > Payment Document - relevant document
Select “Add” icon on invoices to pay
Search the relevant Prepayment invoice > Select the invoice > Apply > OK
Save and Close
AP19 | Applying Debit Memo | Applying a debit memo when making a payment for an invoice | AP19.1 | Applying a debit memo when making a payment for an invoice | Payables > Payments > Create Payment
Enter relevant payment details as a
Enter BU - LB Finance Head Office > Supplier or Party > Supplier Site >Payment Date > Type
Select Disbursement Bank Account > Payment Currency > Payment Method
Payment Process Profile - relevant profile > Payment Document - relevant document
Select “Add” icon on invoices to pay
Search the relevant standard invoice > Select the invoice > Apply >Search the relevant debit note > Apply > OK
Save and Close
AP20 | Processing a single Payment for multiple invoices | Processing a single Payment for multiple invoices | AP20.1 | Processing a single Payment for multiple invoices | Payables > Payments > Create Payment
Enter relevant payment details as a
Enter BU - LB Finance Head Office > Supplier or Party > Supplier Site >Payment Date > Type
Select Disbursement Bank Account > Payment Currency > Payment Method
Payment Process Profile - relevant profile > Payment Document - relevant document
Select “Add” icon on invoices to pay
Search the relevant invoices to pay > Select the invoices > Apply > OK
Save and Close
AP21 | Batch payments | Batch payments | AP21.1 | Creating a payment process template | Payables > Payments > Tasks > Manage Payment Process Request Template > Action > Create
Enter Name
|  |  |  | Selection Criteria | Change “Date Basis” to Due Date > Payment Method - Check > Other details as required
|  |  |  | Payment and Processing Options | Select Payment Date > Disbursement Bank Account > Payment Document > Payment Process Profile > Payment Conversion Rate Type > Other details as required
Select relevant processing opions
Save and Close
|  |  | AP21.2 | Submit Payment Process Request | Tasks > Submit Payment Process Request
Enter Name > Select created template
Submit
|  |  | AP21.3 | Manage Payment Process Requests | Tasks > Manage Payment Process Requests > Search the batch payment
Select Action icon
Select payments you don’t need to pay through this process > Remove > Resume Payment Process
Select Payment Process > Action > Print
Select Payment Process > Go to Action > Record Print Status > Submit > Done
AP22 | Voiding Payments | Voiding Payments | AP22.1 | Voiding Payments | Payables > Payment > Click Task icon >Manage Payment > Search payment from the any given criteria
Select the payment
Action > Void > Select relevant invoice action > Submit
AP23 | Changing payee in payments | Making third-party payments | AP23.1 | Making third-party payments | Payable > Payment > Create Payment
Select Supplier > Select third-party for Payee > Fill other relevant fields
Select the invoice you need to pay for the third-party > Save and Close
AP24 | Paybles Dashboard | Open and Close period | AP24.1 | Open and Close period | Payables > Payables Dashboard
AP25 | Reconciliation | Paybles Ledger Reconciliation | AP25.1 | Paybles Ledger Reconciliation | Payables > Tasks > Payables to Ledger Reconciliation > Click the link
Click Amounts on difference column
AP26 | Period Open/Close | Period Open/Close | AP26.1 | Period Open/Close | General Accounting > Period Close > Select Payables (Open)
|  |  |  | Period Open | Select Future Enterable period
Click “Open Period” icon
|  |  |  | Period Close | Select Open Period
Click "Close Period"