## Sheet1
GAP REGISTER
Client Name |  |  | LSL
Project Name: |  |  | ERP Project
Project Manager Name: |  |  | Saravana S
Job Code |  |  | 1500001
ID | Module Reference | Date Identified | Identified By | Current Status | Priority | Issue Description | Assigned To Owner | Expected Resolution Date | Escalation Required (Y/N)? | Action Steps | Actual Resolution Date | Final Resolution & Rationale
| AR | 2018-09-04 | Madura | Work In Progress | Low | webservice endpoint for customer data from Oracle EBS to PBSA POS | Sayuru | 2018-09-17 | No | PBSA/Softwatch discussing on this |  | PBSA team has given a formulae to generate the Journal Entries Manually or automataed user friendly way in future. Daily Debtors movement = (Total Sales – Total Returns) – (Total Taking – Total Return payments)
2 | AR | 2018-09-04 | Pratheenpan | Closed | Low | Proper format for bank deposit note which is done from PBSA POS so that Oracle EBS can capture it more accurately | Sayuru | 2018-09-17 | No | Receipt No.-Bank Account fomat used | 2018-10-23
3 | Custom | 2018-09-04 | Madura | Closed | Low | Custom Integration Exception Report | Sayuru | 2018-09-17 | No | Exception Report email from Oracle EBS | 2018-10-29 | exception report together with failed open interfaces will be forwarded to oracleebs@lankasathosa.org
5 | Custom | 2018-09-05 | Sayuru | Work In Progress | Medium | data flush policy from intermediate database server used for daily data pulls | Sayuru | 2018-10-01 | No
14 | Finance | 30/10/18 | Procurement DGMs and Managers | Work In Progress | Medium | asset supplier except to PBSA POS (supplier\item creation by Finance) | Sathosa Finance and Procurement Teams | 2018-11-02 | No | fix the responsibilities from Sathosa Finance-need to confirm from management and matrix is initiated in system
16 | Finance | 30/10/18 | Procurement DGMs and Managers | Work In Progress | Medium | Oracle Documentation with workflows | Sathosa Finance and Procurement Teams | 2018-11-02 | No | Oracle EBS process related user guide has to be shared-done and UAT scripts are align to them
4 | Database | 2018-09-05 | Saravana | Open | Medium | Disaster Recovery for currently implementing Oracle ERP project servers | Sayuru | 2018-10-01 | No | Oracle Enterprise Manager Module has capabilities on this or use a manual Open Source Nagios like tool has to be used
8 | Account Payables | 17/09/18 | Umar | Closed | High | after debit memo created in AP Supplier return is approved | Sayuru | 2018-10-01 | No | AME AP approvals are defined | 2018-10-22
9 | Database | 23/09/18 | Fahad | Closed | Medium | data flush policy from APEX server (related to Oracle costing\tax etc.) | Sayuru | 2018-10-01 | No | duplicated ID 5
10 | Purchasing | 16/09/18 | Sayuru/Steven | Closed | Medium | data from outlets in old PBSA - IP addresses list required (outlets IP, HO IP after api work) | Sayuru | 2018-10-01 | No | 12 outlets provided with summary data only | 2018-10-30
11 | Inventory | 19/09/18 | Sayuru/Steven | Closed | Medium | .EBS Stores ID from CoA but PBSA POS is different. .Item Master with UoM .Initial upload of Supplier\Product GUIDs | Sayuru/Steven | 2018-10-01 | No | data dump requetsed and agreed | 2018-10-30
12 | Purchasing | 17/09/18 | Madura/Sayuru | Closed | Critical | Confirm the PO reference in PR Lines and Supplier Return Request | Sayuru | 2018-10-01 | No | data with a change in PBSA POS new version | 2018-10-12
6 | Custom | 2018-09-05 | Sayuru | Open | Medium | Research and Technology Development(R&TD) inputs from Sathosa\softwatch\Oracle Tech Team\PBSA (eg. Data communication security) | Sayuru | 2018-10-01 | No | data security only by whitelist IP but communication protocol can be evaded
7 | Custom | 2018-09-05 | Madura | Open | Medium | dashboard for daily data analysis | Sayuru | 2018-10-01 | No | APEX server have alternatives and need their requirements on Dashboards
13 | Fixed Asset | 30/10/18 | Procurement DGMs and teams | Open | Medium | Engineering & Operations Procurement to PO Dept. (Spec from FA Finance to Procurement do purchasing quality check\GRN to FA Procurement | Sathosa Finance and Procurement Teams | 2018-11-02 | No | Segreration agreed and need to communicated with Oracle ERP implementation
15 | Fixed Asset | 30/10/18 | Procurement DGMs and Managers | Open | Medium | Outlet level services from PBSA POS for asset related expenses | Sathosa Finance and Procurement Teams | 2018-12-16 | No | SKU level category and services defined and submit to Oracle PBSA integration
17 | IT\Networking | 15/10/18 | IT\KPMG | Open | Medium | SSO login for Oracle ERP and related APEX developed (TBD) | Sathosa and KPMG Tech\DBA | 2018-12-15 | No | Overview of Single Sign-On Integration Options for Oracle E-Business Suite (Doc ID 1388152.1)
18 | Tech | 2018-01-10 | Sathosa\KPMG | Open | Low | Limited License per module | Sathosa and KPMG Tech\DBA | 2018-12-15 | No | How to Get the terminal ID for the Machine From Which a User is Logged to E-Business Suite Applications? (Doc ID 751658.1) How To Find The IP Address Of The Client Machine From Where A Particular Forms User Is Connected ? (Doc ID 879092.1) |  | Oracle Application session is mapped to fnd_profile.value('LOGIN_ID'). It is machanism to find IP of the logged in user.
19 | AP | 26/11/2018 | Sathosa | Closed | Medium | Creditor should be recognised at the Point of GRN without any manual involvement. | Sathosa and KPMG | 2018-11-26 | No | Functional Payable invoice validation program needs to be schedule and run from background
20 | AP | 26/11/2018 | Sathosa | Closed | Medium | Supplier payment validity screen should be in supplier wise not in the batch wise. | Sathosa and KPMG | 2018-11-26 | No | Functional-Remove the invoice batch name and search with different search criteria like dates and supplier etc.
21 | AP | 26/11/2018 | Sathosa | Work In Progress | Medium | There should be unique GRN Number in both systems (Oracle & PBSA POS). | Sathosa and KPMG | 2018-11-26 | No | Functional-GRN Print will be included with the Shop\Warehouse PBSA POS GRN number so that requested information can be cross checked with GRN Print, and AP Invoice
22 | AP | 26/11/2018 | Sathosa | Work In Progress | Medium | Transport income, Loyalty Income, Electricity Income should be recognised @ the GRN point. | Sathosa and KPMG | 2018-11-26 | No | Functional-Needs a functional distribution set level setup
23 | AP | 26/11/2018 | Sathosa | Closed | Medium | Supplier market return number should be unique in both systems and it should be same with the supplier number. | Sathosa and KPMG | 2018-11-26 | No | Functional-supplier return related debit memo is in the same invoice employee wise batch with same supplier return number which is the RA number in the PBSA POS
24 | AP | 26/11/2018 | Sathosa | Open | Medium | Need pilot run. | Sathosa and KPMG | 2018-11-26 | No | Functional-before the UAT the listed gaps will be show-cased
25 | AP | 26/11/2018 | Sathosa | Work In Progress | Medium | Journal entries creation process .DR & CR accumulate amount should be show in the top of the screen | Sathosa and KPMG | 2018-11-26 | No | Functional-work around suggested to use Oracle Web ADI which is an excel upload
26 | AP | 26/11/2018 | Sathosa | Work In Progress | Medium | Other payments bulk entry should post through the excel format.e.g-security charges/electricity/transport-shop wise | Sathosa and KPMG | 2018-11-26 | No | Functional-since it is not a recurring task customize simple ap invoce upload excel solution has been under development
27 | AP | 26/11/2018 | Sathosa | Open | Medium | Supplier journal process-debit / credit notes | Sathosa and KPMG | 2018-11-26 | No | Functional
28 | AP | 26/11/2018 | Sathosa | Closed | Medium | Idle time for voucher creation process????? | Sathosa and KPMG | 2018-11-26 | No | Functional-we will show case this with high volume of invoces in a payment batch. Oracle ERP is well tuned to handle this kind of processes
29 | AP | 26/11/2018 | Sathosa | Closed | Medium | GL code digits so long. | Sathosa and KPMG | 2018-11-26 | No | Functional-This is the initial\Finalise CoA descriptions
30 | AP | 26/11/2018 | Sathosa | Work In Progress | Medium | Supplier pending return report facility-provision & grocery category wise | Sathosa and KPMG | 2018-11-26 | No | Functional-Usually the supplier returns are synced to Oracle Payables daily(1) and interfaced to Oracle Payable(2). Execption Report will fullfill this requirement
31 | AP | 26/11/2018 | Sathosa | Open | Medium | Supplier returns process not clear | Sathosa and KPMG | 2018-11-26 | No | Functional-Will do a demo on this while show-casing the gap listed
32 | AP | 26/11/2018 | Sathosa | Open | Medium | Needs training again for payments section | Sathosa and KPMG | 2018-11-26 | No | Functional-Will do a demo on this while show-casing the gap listed
33 | AP | 26/11/2018 | Sathosa | Closed | Medium | Other Payments invoice number creation should be generate automate not manually | Sathosa and KPMG | 2018-11-26 | No | Functional-Done in Payable invoice form
34 | FA | 26/11/2018 | Sathosa | Open | Medium | Bulk entry should be posted through the excel format | Sathosa and KPMG | 2018-11-26 | No | Functional-Oracle Web ADI is available for this task and can be used with serial number\tag number etc.
35 | FA | 26/11/2018 | Sathosa | Open | Medium | System automated Assets Number | Sathosa and KPMG | 2018-11-26 | No | Functional-Oracle generated number will be physical asset number
36 | FA | 26/11/2018 | Sathosa | Open | Medium | Bulk Posting option | Sathosa and KPMG | 2018-11-26 | No | Functional-Oracle Web ADI is available for this task and can be used with serial number\tag number etc.
37 | GL | 26/11/2018 | Sathosa | Closed | Medium | Total sales should be captured from PBSA POS as per sales settlements base Such as Cash Sales, Credit Sales, Card Sales and Gift Voucher Sales. | Sathosa and KPMG | 2018-11-26 | No | Functional-JE batches are generated on daily basis for this purpose
38 | GL | 26/11/2018 | Sathosa | Open | Medium | Card Settlement should be captured by type of bank card machine such as BOC,HNB, Commercial & Amex. | Sathosa and KPMG | 2018-11-26 | No | Functional-Receipt Number-Branch will hit the JE line with required bank and branch A/C
39 | GL | 26/11/2018 | Sathosa | Open | Medium | Tax (VAT & NBT) amount can be recognized as item wise. | Sathosa and KPMG | 2018-11-26 | No | Functional-need to use JE reference and breakdown in a separate report
40 | GL | 26/11/2018 | Sathosa | Work In Progress | Medium | Debtor settlements should be capture from PBSA POS | Sathosa and KPMG | 2018-11-26 | No | Functional-Debtor movement solution and it is not sufficient so that PBSA POS api change required. Already discussions are going on
41 | GL | 26/11/2018 | Sathosa | Work In Progress | Medium | J/E should be auto posted to the system at the time of approvals given | Sathosa and KPMG | 2018-11-26 | No | Functional
42 | GL | 26/11/2018 | Sathosa | Closed | Medium | Deposits by outlets should be captured from PBSA POS | Sathosa and KPMG | 2018-11-26 | No | Functional-JE Batches are available for this purpose
43 | GL | 26/11/2018 | Sathosa | Open | Medium | Other Income should be captured from PBSA POS | Sathosa and KPMG | 2018-11-26 | No | Functional-need PBSA POS api changes
44 | AR | 26/11/2018 | Sathosa | Closed | Medium | We need system automated Invoice & Receipt Numbers | Sathosa and KPMG | 2018-11-26 | No | Functional-GRN receipts and payable invoice numbers are systematically sequenced
45 | AR | 26/11/2018 | Sathosa | Closed | Medium | Invoice & Receipt print | Sathosa and KPMG | 2018-11-26 | No | Functional-already developed
46 | AR | 26/11/2018 | Sathosa | Closed | Medium | Invoice should includ details not summary (Outlets wise income) | Sathosa and KPMG | 2018-11-26 | No | Functional-invoices are included with line and distribution details
47 | AR | 26/11/2018 | Sathosa | Open | Medium | Invoice should be included discount amount | Sathosa and KPMG | 2018-11-26 | No | Functional-need a robust criteria
48 | AR | 26/11/2018 | Sathosa | Work In Progress | Medium | Receipt should show the type of settlement (Cash or Cheque) | Sathosa and KPMG | 2018-11-26 | No | Functional-receipt print is tagged with payment type
49 | CM | 26/11/2018 | Sathosa | Open | Medium | Need a solution to People’s bank Savings account system reconciliation | Sathosa and KPMG | 2018-11-26 | No | Functional-CM module
50 | Other | 26/11/2018 | Sathosa | Work In Progress | Medium | More practical session needed | Sathosa and KPMG | 2018-11-26 | No | Functional-needs to install windows sp1 on client PCs
51 | Custom | 2019-01-31 | Sathosa\KPMG Technical | Open | High | printer architecture - Setup Instructions for Printing from Oracle Cloud (Doc ID 1964157.1) | Sathosa and KPMG | 2019-01-31 | No | lpstat -d lpadmin -d Epson-Dot-Matrix -d Epson-Dot-Matrix IX_PRINTING="/testfs/TEST/fs1/EBSapps/appl/fnd/12.0.0/resource/ixlib.cfg" --related /etc/cups/cupsd.conf --adding the printer server /usr/sbin/lpadmin -p LaserJet(virtual printer server/EBS defined printer) -E -v socket://cupsserevr.cupsexample.com -m laserjet.ppd --adding the printer clients /usr/sbin/lpadmin -p LaserJet1,2,...(Windows Client PC based IP printers) -E -v socket://192.168.16.1...xxxx -m laserjet.ppd --body starts of /etc/cups/client.conf ServerName cupsserevr.cupsexample.com --body ends --get printers installed in CUPS lpinfo -m --get the default printer name from windows PC smbclient '\\LKKTS_L046\Users\sjayasinghe1\Downloads\' -c 'lcd /tmp; cd test_folder; get default_printer.txt' -U sjayasitbne1%1qaz67
Note on A6: • ID: A unique ID number used to identify the issue in the Gap Register log.
Note on B6: Module Reference: This should include relevant module for reference
Note on C6: • Date Identified: This column should be populated with the date that the issue was identified.
Note on D6: • Entered By: This column should be populated by the name of the individual who first identified the issue.
Note on E6: • Current Status: This column should be populated with the issue's current status. o Open: The issue is currently open but has not yet been addressed. o Work In Progress: The issue is being actively worked to develop a resolution. o Closed: The issue is no longer considered an active project threat and can be closed with or without resolution. Some other potential options include: o Late: The issue resolution is not yet resolved and it is past the expected resolution date. o On Hold: The issue has been put on hold. o Combined: Two issues found to be similar have been combined.
Note on F6: • Priority: This column should be populated with the priority of the issue. Valid options include the following: High, Medium, Low. These are defined as follows: o Critical: Issue will stop project progress if not resolved. o High: Issue will likely move the project back in terms of budget or timeline, or will materially affect quality or scope. o Medium: Issue will have material effect on project, has potential to be moved to high category and/or requires significant resources to manage. o Low: Issue is expected to have a moderate effect on the project, but will require resources to address.
Note on G6: • Issue Description: This column should be populated with a description of the issue.
Note on H6: • Assigned To Owner: This column should be populated by the name of the issues owner. The individual most responsible for working towards resolving the issue.
Note on I6: • Expected Resolution Date: This column should be populated with the date that the issue is expected to be resolved.
Note on J6: • Escalation Required (Y/N): This column should be populated with “Yes” if the program/project manager feels an issue needs to be escalated and “No” if escalation is not needed to resolve the issue.
Note on K6: • Action Steps: This column should be populated with the proposed steps to address the issue. Examples include, but are not limited to, developing alternatives analysis or submitting a change request.
Note on L6: • Actual Resolution Date: This column should be populated with the date that the issue was actually resolved.
Note on M6: • Final Resolution & Rationale: This column should be populated with a description of the final resolution & rationale of the issue. The resolution may be expressed in terms of one or more of the following: schedule, scope, resources, and space. The resolution description should also include a reference to the milestones impacted.